## High level
Task	Amount	Effort ( Days)	Show working	Reference	%age complete
Evaluate Gutenberg's compatibility with own plugin / theme	100	10	10 per day	Source repos under bobbingwide
Convert shortcodes to blocks	200	342		See Shortcodes sheet
Evaluate Gutenberg's compatibility with site	250			Subdirectory intsalls
Migrate content to block editor	???

## Unknowns
Unknowns
How to correctly implement issues with “keys”
How to access options from the REST API
How to lazy load JS / CSS
How to lazy load REACT code
How to perform REST queries
How to internationalize
How to support JS in metaboxes
How to control block conversion
How and when to implement logic for deprecated blocks
How to test JS code
How to automatically migrate content?

## Risks
Risks	Likelihood	Severity	Mitigation?
Unknowns
Esitmates incorrect
Gutenberg not delivered in core
Gutenberg breaks site
Classic-editor breaks site
User breaks site
Updated plugin / theme breaks site
Estimates not possible

Likelihood	Severity
Certain
Likely
Possible
Unlikely
Rare

## Shortcodes
				342
Shortcode	Desc	#parameters	Component	Inline/Block	Convert?	Dynamic	Hours	Days
nivo	Display the nivo slideshow for attachments or other post types.	29	oik-nivo-slider	Block			42	6
bw_cycle	Display pages using jQuery cycle	23	oik	Block			42	6
bw_popup	Display a popup after a timed delay	23	oik-popup	Block			42	6
bw_attachments	List attachments with links	20	oik	Block			42	6
bw_images	Display attached images	20	oik	Block			42	6
bw_pages	Display page thumbnails and excerpts as links	20	oik	Block			42	6
bw_testimonials	Display testimonials	20	oik-testimonials	Block			42	6
bw_list	Simple list of pages/posts or custom post types	19	oik	Block			42	6
bw_navi	Simple paginated list	19	oik	Block			42	6
bw_otd	Display 'On this day' in history related content	19	oik-dates	Block			42	6
bw_pdf	Display attached PDF files	19	oik	Block			42	6
bw_table	Display custom post data in a tabular form	19	oik	Block			42	6
bw_thumbs	List pages as fluid thumbnail links	19	oik	Block			42	6
bw_portfolio	Display matched portfolio files	18	oik	Block			42	6
bw_posts	Display posts	18	oik	Block			42	6
bw_accordion	Display posts in an accordion	17	oik				42	6
bw_tabs	Display posts in tabbed blocks	17	oik				42	6
bw_tree	Simple tree of pages/posts or custom post types	17	oik				42	6
playlist	Playlist	12	core				21	3
paypal	Paypal shortcodes	11	oik				21	3
gallery	Display the attached images in a gallery	10	core				21	3
bw_iframe	Embed a page in an iframe	9	oik				21	3
bw_emergency	Emergency telephone number	8	oik				21	3
bw_fax	Fax number	8	oik				21	3
bw_jq	Perform a jQuery method	8	oik				21	3
bw_mob	Mobile phone number (inline)	8	oik				21	3
bw_mobile	Mobile phone number (block)	8	oik				21	3
bw_show_googlemap	Show Google map [bw_show_googlemap]	8	oik				21	3
bw_skype	Skype name	8	oik				21	3
bw_tel	Telephone number (inline)	8	oik				21	3
bw_telephone	Telephone number (block)	8	oik				21	3
bw_users	Display information about site users	8	oik-user				21	3
video	Embed video files	7	core				21	3
bw_code	Display the help and syntax for a shortcode	6	oik				21	3
bw_csv	Display CSV data in a table or list	6	oik-bob-bing-wide				21	3
bw_email	Email primary contact (formal)	6	oik				21	3
bw_mailto	Mailto (inline)	6	oik				21	3
post_comments	Display link to post comments	6	oik-sc-help				21	3
bw_background	Use attached image as the background	5	oik-css				21	3
bw_block	Format an Artisteer block	5	oik				21	3
bw_contact_button	Contact form button	5	oik				21	3
bw_contact_form	Display a contact form for the specific user	5	oik				21	3
bw_copyright	Format a Copyright statement	5	core				21	3
bw_countdown	Countdown timer	5	oik				21	3
bw_link	Display a link to a post.	5	oik				21	3
bw_plug	Show plugin information	5	oik-bob-bing-wide				21	3
bw_related	Display related content	5	oik-fields				21	3
footer_backtotop	Produces the 'Return to Top' link	5	oik-sc-help				21	3
github	Link to GitHub	5	oik-bob-bing-wide				21	3
audio	Displays uploaded audio file as an audio player	4	oik-sc-help	Block			7	1
bw_bookmarks	List bookmarks	4	oik				7	1
bw_button	Show a link as a button	4	oik				7	1
bw_logo	Display the company logo	4	oik				7	1
bw_qrcode	Display an uploaded QR code image	4	oik				7	1
caption	Display the caption for an image. Standard WordPress shortcode	4	core				7	1
clone	Display the clone tree/form for a post	4	oik-clone				7	1
codes	Create links to related shortcodes	4	oik-shortcodes				7	1
cookies	Display table of cookies	4	Cookie-cat	Block			7	1
footer_copyright	Display copyright notice	4	oik-sc-help				7	1
post_date	Display post publication date	4	oik-sc-help				7	1
post_modified_date	Display post last modified date	4	oik-sc-help				7	1
post_modified_time	Display post last modified time	4	oik-sc-help				7	1
post_terms	Display linked post taxonomy terms list	4	oik-sc-help				7	1
post_time	Display post publication time	4	oik-sc-help				7	1
wp_caption	Display the caption for an image. Standard WordPress shortcode	4	core				7	1
apis	Link to API definitions	3	oik-shortcodes	Block			7	1
bw_address	Display the address	3	oik				7	1
bw_api	Dynamic API syntax help	3	oik-shortcodes				7	1
bw_field	Format custom fields without labels	3	oik-fields				7	1
bw_follow_me	Display defined social media follow me links	3	oik				7	1
bw_new	Display a form to create a new post	3	oik-fields				7	1
bw_page	Add page button	3	oik-bob-bing-wide				7	1
bw_post	Add Post button	3	oik-bob-bing-wide				7	1
bw_terms	Display taxonomy terms links	3	oik-a2z				7	1
bw_tides	Display times and tides for a UK location	3	uk-tides				7	1
bw_wtf	WTF	3	oik				7	1
classes	Link to class definitions	3	oik-shortcodes				7	1
cloned	Display clones of this content	3	oik-clone				7	1
embed	Embed media	3	core				7	1
files	Link to files definitions	3	oik-shortcodes				7	1
footer_loginout	Display link to WordPress.	3	oik-sc-help				7	1
hooks	Link to hook definitions	3	oik-shortcodes				7	1
post_categories	Display category links list	3	oik-sc-help				7	1
post_edit	Display edit post link	3	oik-sc-help				7	1
post_tags	Display tag links list	3	oik-sc-help				7	1
stag	Start a tag	3	core				7	1
bw_blockquote	Format a blockquote	2	oik				7	1
bw_cite	Cite a blockquote	2	oik				7	1
bw_count	Count posts for the selected post type	2	oik				7	1
bw_css	Add internal CSS styling	2	oik-css				7	1
bw_dash	Display a dash icon	2	oik-cons				7	1
bw_fields	Format custom fields	2	Oik-fields	Block			7	1
bw_geshi	Generic Syntax Highlighting	2	oik-css				7	1
bw_graphviz	Display a GraphViz diagram	2	oik-bob-bing-wide				7	1
bw_group	Display summary of selected items	2	oik-fields				7	1
bw_login	Display the login form or protected content	2	oik				7	1
bw_more	Read more button to progressively reveal content	2	oik-read-more				7	1
bw_option	Display the value of an option field	2	oik-bob-bing-wide				7	1
bw_user	Display information about a user	2	oik-user				7	1
bwtrace	Trace facility form	2	oik				7	1
div	start a &lt;div&gt; tag	2	core				7	1
footer_childtheme_link	Display link to child theme	2	Oik-sc-help	Block			7	1
footer_genesis_link	Display link to the Genesis Framework.	2	oik-sc-help				7	1
footer_studiopress_link	Display link to StudioPress.	2	oik-sc-help				7	1
footer_wordpress_link	Display link to WordPress.	2	oik-sc-help				7	1
oikp_download	Produce a download button for a plugin	2	oik-plugins				7	1
oikth_download	Produce a download button for a theme	2	oik-themes				7	1
post_author	Display post author name	2	oik-sc-help				7	1
post_author_link	Display post author link	2	oik-sc-help				7	1
post_author_posts_link	Display link to author's posts	2	oik-sc-help				7	1
sdiv	Start a div	2	core				7	1
api	Simple API link	1	oik-shortcodes	Inline			7	1
bw	Expand to the logo for Bobbing Wide	1	oik	Inline			7	1
bw_autop	Dynamically re-enable/disable automatic paragraph generation	1	oik-css				7	1
bw_blog	Select blog to process	1	oik-ms				7	1
bw_blogs	List blogs or display content for selected blogs	1	oik-ms				7	1
bw_codes	Display the currently available shortcodes	1	oik				7	1
bw_contact	Primary contact name	1	oik				7	1
bw_directions	Display a 'Google directions' button.	1	oik				7	1
bw_geo	Latitude and Longitude	1	oik				7	1
bw_parent	Display a link back to the parent page	1	oik				7	1
bw_rwd	Dynamically generate oik responsive web design CSS classes	1	oik-rwd				7	1
etag	End a tag started with [stag]	1	core				7	1
file	Display reference for a file	1	oik-shortcodes				7	1
29608	trac_29608	0	core				7	1
artisteer	Styled form of Artisteer	0	oik-bob-bing-wide	Inline			7	1
bp	Styled form of BuddyPress	0	oik-bob-bing-wide	Inline			7	1
bw_abbr	Format an abbreviation	0	oik				7	1
bw_acronym	Format an acronym	0	oik				7	1
bw_action	bw_shortcode_event	0	oik-bob-bing-wide				7	1
bw_admin	Display the Admin contact name	0	oik				7	1
bw_alt_slogan	Alternative slogan	0	oik				7	1
bw_business	Display your Business name	0	oik				7	1
bw_company	Company name	0	oik				7	1
bw_crumbs	Display breadcrumbs	0	oik-bob-bing-wide				7	1
bw_domain	Display the domain name	0	oik				7	1
bw_eblock	end a [bw_block]	0	oik				7	1
bw_editcss	Edit Custom CSS file button	0	oik				7	1
bw_email_signature	Format the email signature	0	core				7	1
bw_facebook	Facebook link	0	oik				7	1
bw_flickr	Flickr link	0	oik				7	1
bw_formal	Formal company name	0	oik				7	1
bw_google	Google+ link	0	oik				7	1
bw_google_plus	Google+ link	0	oik				7	1
bw_google-plus	Google+ link	0	oik				7	1
bw_googleplus	Google+ link	0	oik				7	1
bw_instagram	Follow me on Instagram	0	oik				7	1
bw_linkedin	Follow me on LinkedIn	0	oik				7	1
bw_loginout	Display the Login or Logout link	0	oik				7	1
bw_picasa	Follow me on Picasa	0	oik				7	1
bw_pinterest	Follow me on Pinterest	0	oik				7	1
bw_power	Powered by WordPress	0	oik				7	1
bw_qv	bw_shortcode_event	0	core				7	1
bw_register	Display a link to the Registration form	0	oik	Block			7	1
bw_rpt	bw_shortcode_event	0	oik-bob-bing-wide				7	1
bw_search	Display search form	0	oik-bob-bing-wide				7	1
bw_slogan	Primary slogan	0	oik				7	1
bw_squeeze	bw_shortcode_event	0	oik-squeeze				7	1
bw_text	bw_shortcode_event	0	oik-bob-bing-wide				7	1
bw_twitter	Follow me on Twitter	0	oik				7	1
bw_wpadmin	Site: link to wp-admin	0	oik				7	1
bw_youtube	Follow me on YouTube	0	oik				7	1
bwtroff	Force trace off	0	oik				7	1
bwtron	Force trace on	0	oik				7	1
clear	Clear divs	0	core				7	1
drupal	bw_shortcode_event	0	oik-bob-bing-wide				7	1
dumptag	trac_29608_shortcode_dumptag	0	core				7	1
ediv	end a &lt;div&gt; with &lt;/div&gt;	0	core				7	1
footer_home_link	genesis_footer_home_link_shortcode	0	core				7	1
footer_site_title	genesis_footer_site_title_shortcode	0	core				7	1
gpslides	Display a Slideshow Gallery Pro slideshow	0	oik				7	1
hook	bw_shortcode_event	0	oik-shortcodes				7	1
lartisteer	Link to Artisteer	0	oik-bob-bing-wide				7	1
lbp	Link to BuddyPress	0	oik-bob-bing-wide				7	1
lbw	Link to Bobbing Wide sites	0	oik				7	1
ldrupal	Link to drupal.org	0	oik-bob-bing-wide				7	1
loik	Link to [oik]-plugins	0	oik				7	1
lwp	Link to WordPress.org	0	oik-bob-bing-wide				7	1
lwpms	Link to WordPress Multi Site	0	oik-bob-bing-wide				7	1
md	Format Markdown	0	oik-shortcodes				7	1
ngslideshow	NextGen gallery slideshow	0	core				7	1
noautop	trac_29608_noautop	0	core				7	1
OIK	Spells out the <span class="bw_oik"><abbr title="OIK Information Kit">oik</abbr></span> backronym	0	oik	Inline			7	1
oik	Expand to the logo for oik	0	oik				7	1
oik_edd_apikey	get API key form for EDD	0	oik-edd				7	1
paragraph	trac_29608_shortcode_paragraph	0	core				7	1
parsed_source	bw_shortcode_event	0	oik-shortcodes				7	1
sediv	Start and end a div	0	core				7	1
wp	Display a styled form of WordPress.	0	oik-bob-bing-wide				7	1
wpms	Styled form of WordPress Multi Site	0	oik-bob-bing-wide				7	1

## Hours
Parameter count to Size to Hours				Total hrs	7	21	42
Count	Size	Hours		Task	Small	Med	Large
0	Small	7		Design/spec	1	3	7
1	Small	7		Code	2	7	14
2	Small	7		Test	2	7	14
3	Small	7		Document	1	3	6
4	Small	7		Release	1	1	1
5	Med	21
6	Med	21		Days	1	3	6
7	Med	21
8	Med	21
9	Med	21
10	Med	21
11	Med	21
12	Med	21
13	Med	21
14	Med	21
15	Med	21
16	Med	21
17	Large	42
18	Large	42
19	Large	42
20	Large	42
21	Large	42
22	Large	42
23	Large	42
24	Large	42
25	Large	42
26	Large	42
27	Large	42
28	Large	42
29	Large	42
30	Large	42