## High level
Task	Amount	Effort ( Days)	Adjusted	Show working	Reference	%age complete
Evaluate Gutenberg's compatibility with own plugin / theme	100	10		10 per day	Source repos under bobbingwide – Components
Convert shortcodes to blocks	200	342	203		See Shortcodes sheet
Evaluate Gutenberg's compatibility with site	250		40		Subdirectory installs
Migrate content to block editor	???

## Unknowns
Unknowns
How to correctly implement issues with “keys”
How to access options from the REST API
How to lazy load JS / CSS
How to lazy load REACT code
How to perform REST queries
How to internationalize
How to support JS in metaboxes
How to control block conversion
How and when to implement logic for deprecated blocks
How to test JS code
How to automatically migrate content?

## Risks
Risks	Likelihood	Severity	Mitigation?
Unknowns
Estimates incorrect
Gutenberg not delivered in core
Gutenberg breaks site
Classic-editor breaks site
User breaks site
Updated plugin / theme breaks site
Estimates not possible

Likelihood	Severity
Certain
Likely
Possible
Unlikely
Rare

## Shortcodes
				342	203
Shortcode	Desc	#parameters	Component	Inline/Block	Convert?	Dynamic	Hours	Days	Adjusted
nivo	Display the nivo slideshow for attachments or other post types.	29	oik-nivo-slider	Block	1		42	6	6
bw_cycle	Display pages using jQuery cycle	23	oik	Block	1		42	6	6
bw_popup	Display a popup after a timed delay	23	oik-popup	Block	1		42	6	6
bw_attachments	List attachments with links	20	oik	Block	1		42	6	6
bw_images	Display attached images	20	oik	Block	1		42	6	6
bw_pages	Display page thumbnails and excerpts as links	20	oik	Block	1		42	6	6
bw_testimonials	Display testimonials	20	oik-testimonials	Block	1		42	6	6
bw_list	Simple list of pages/posts or custom post types	19	oik	Block	1		42	6	6
bw_navi	Simple paginated list	19	oik	Block	1		42	6	6
bw_otd	Display 'On this day' in history related content	19	oik-dates	Block	1		42	6	6
bw_pdf	Display attached PDF files	19	oik	Block	1		42	6	6
bw_table	Display custom post data in a tabular form	19	oik	Block	1		42	6	6
bw_thumbs	List pages as fluid thumbnail links	19	oik	Block	1		42	6	6
bw_portfolio	Display matched portfolio files	18	oik	Block	1		42	6	6
bw_posts	Display posts	18	oik	Block	1		42	6	6
bw_accordion	Display posts in an accordion	17	oik	Block	1		42	6	6
bw_tabs	Display posts in tabbed blocks	17	oik	Block	1		42	6	6
bw_tree	Simple tree of pages/posts or custom post types	17	oik	Block	1		42	6	6
playlist	Playlist	12	core	Block	0		21	3	0
paypal	Paypal shortcodes	11	oik	Block	1		21	3	3
gallery	Display the attached images in a gallery	10	core	Block	0		21	3	0
bw_iframe	Embed a page in an iframe	9	oik	Block	0		21	3	0
bw_emergency	Emergency telephone number	8	oik	Block	1		21	3	3
bw_fax	Fax number	8	oik	Block	1		21	3	3
bw_jq	Perform a jQuery method	8	oik	Block	0		21	3	0
bw_mob	Mobile phone number (inline)	8	oik	Inline	1		21	3	3
bw_mobile	Mobile phone number (block)	8	oik	Block	1		21	3	3
bw_show_googlemap	Show Google map [bw_show_googlemap]	8	oik	Block	1		21	3	3
bw_skype	Skype name	8	oik	Block	1		21	3	3
bw_tel	Telephone number (inline)	8	oik	Inline	1		21	3	3
bw_telephone	Telephone number (block)	8	oik	Block	1		21	3	3
bw_users	Display information about site users	8	oik-user	Block	1		21	3	3
video	Embed video files	7	core	Block	0		21	3	0
bw_code	Display the help and syntax for a shortcode	6	oik	Block	1		21	3	3
bw_csv	Display CSV data in a table or list	6	oik-bob-bing-wide	Block	1		21	3	3
bw_email	Email primary contact (formal)	6	oik	Inline	1		21	3	3
bw_mailto	Mailto (inline)	6	oik	Inline	1		21	3	3
post_comments	Display link to post comments	6	oik-sc-help	Block	0		21	3	0
bw_background	Use attached image as the background	5	oik-css	Block	0		21	3	0
bw_block	Format an Artisteer block	5	oik	Block	0		21	3	0
bw_contact_button	Contact form button	5	oik	Inline	0		21	3	0
bw_contact_form	Display a contact form for the specific user	5	oik	Block	1		21	3	3
bw_copyright	Format a Copyright statement	5	core	Block	1		21	3	3
bw_countdown	Countdown timer	5	oik	Block	1		21	3	3
bw_link	Display a link to a post.	5	oik	Inline	0		21	3	0
bw_plug	Show plugin information	5	oik-bob-bing-wide	Mixed	1		21	3	3
bw_related	Display related content	5	oik-fields	Block	1		21	3	3
footer_backtotop	Produces the 'Return to Top' link	5	oik-sc-help	Block	0		21	3	0
github	Link to GitHub	5	oik-bob-bing-wide	Inline	1		21	3	3
audio	Displays uploaded audio file as an audio player	4	oik-sc-help	Block	0		7	1	0
bw_bookmarks	List bookmarks	4	oik	Block	0		7	1	0
bw_button	Show a link as a button	4	oik	Block	0		7	1	0
bw_logo	Display the company logo	4	oik	Block	1		7	1	1
bw_qrcode	Display an uploaded QR code image	4	oik	Block	0		7	1	0
caption	Display the caption for an image. Standard WordPress shortcode	4	core	Block	0		7	1	0
clone	Display the clone tree/form for a post	4	oik-clone	Block	0		7	1	0
codes	Create links to related shortcodes	4	oik-shortcodes	Mixed	0		7	1	0
cookies	Display table of cookies	4	Cookie-cat	Block	0		7	1	0
footer_copyright	Display copyright notice	4	oik-sc-help	Block	0		7	1	0
post_date	Display post publication date	4	oik-sc-help	Block	0		7	1	0
post_modified_date	Display post last modified date	4	oik-sc-help	Block	0		7	1	0
post_modified_time	Display post last modified time	4	oik-sc-help	Block	0		7	1	0
post_terms	Display linked post taxonomy terms list	4	oik-sc-help	Block	0		7	1	0
post_time	Display post publication time	4	oik-sc-help	Block	0		7	1	0
wp_caption	Display the caption for an image. Standard WordPress shortcode	4	core	Block	0		7	1	0
apis	Link to API definitions	3	oik-shortcodes	Block	0		7	1	0
bw_address	Display the address	3	oik	Block	1		7	1	1
bw_api	Dynamic API syntax help	3	oik-shortcodes	Block	1		7	1	1
bw_field	Format custom fields without labels	3	oik-fields	Mixed	1		7	1	1
bw_follow_me	Display defined social media follow me links	3	oik	Block	1		7	1	1
bw_new	Display a form to create a new post	3	oik-fields	Block	0		7	1	0
bw_page	Add page button	3	oik-bob-bing-wide	Inline	0		7	1	0
bw_post	Add Post button	3	oik-bob-bing-wide	Inline	0		7	1	0
bw_terms	Display taxonomy terms links	3	oik-a2z	Block	1		7	1	1
bw_tides	Display times and tides for a UK location	3	uk-tides	Block	1		7	1	1
bw_wtf	WTF	3	oik	Block	0		7	1	0
classes	Link to class definitions	3	oik-shortcodes	Block	0		7	1	0
cloned	Display clones of this content	3	oik-clone	Block	0		7	1	0
embed	Embed media	3	core	Block	0		7	1	0
files	Link to files definitions	3	oik-shortcodes	Block	0		7	1	0
footer_loginout	Display link to WordPress.	3	oik-sc-help	Block	0		7	1	0
hooks	Link to hook definitions	3	oik-shortcodes	Block	0		7	1	0
post_categories	Display category links list	3	oik-sc-help	Block	0		7	1	0
post_edit	Display edit post link	3	oik-sc-help	Block	0		7	1	0
post_tags	Display tag links list	3	oik-sc-help	Block	0		7	1	0
stag	Start a tag	3	core	Inline	0		7	1	0
bw_blockquote	Format a blockquote	2	oik	Block	0		7	1	0
bw_cite	Cite a blockquote	2	oik	Block	0		7	1	0
bw_count	Count posts for the selected post type	2	oik	Inline	0		7	1	0
bw_css	Add internal CSS styling	2	oik-css	Block	1		7	1	1
bw_dash	Display a dash icon	2	oik-cons	Mixed	1		7	1	1
bw_fields	Format custom fields	2	Oik-fields	Block	1		7	1	1
bw_geshi	Generic Syntax Highlighting	2	oik-css	Block	1		7	1	1
bw_graphviz	Display a GraphViz diagram	2	oik-bob-bing-wide	Block	1		7	1	1
bw_group	Display summary of selected items	2	oik-fields	Block	0		7	1	0
bw_login	Display the login form or protected content	2	oik	Block	1		7	1	1
bw_more	Read more button to progressively reveal content	2	oik-read-more	Block	1		7	1	1
bw_option	Display the value of an option field	2	oik-bob-bing-wide	Inline	0		7	1	0
bw_user	Display information about a user	2	oik-user	Block	1		7	1	1
bwtrace	Trace facility form	2	oik	Block	0		7	1	0
div	start a &lt;div&gt; tag	2	core	Block	0		7	1	0
footer_childtheme_link	Display link to child theme	2	Oik-sc-help	Block	0		7	1	0
footer_genesis_link	Display link to the Genesis Framework.	2	oik-sc-help	Block	0		7	1	0
footer_studiopress_link	Display link to StudioPress.	2	oik-sc-help	Block	0		7	1	0
footer_wordpress_link	Display link to WordPress.	2	oik-sc-help	Block	0		7	1	0
oikp_download	Produce a download button for a plugin	2	oik-plugins	Block	0		7	1	0
oikth_download	Produce a download button for a theme	2	oik-themes	Block	0		7	1	0
post_author	Display post author name	2	oik-sc-help	Block	0		7	1	0
post_author_link	Display post author link	2	oik-sc-help	Block	0		7	1	0
post_author_posts_link	Display link to author's posts	2	oik-sc-help	Block	0		7	1	0
sdiv	Start a div	2	core	Block	0		7	1	0
api	Simple API link	1	oik-shortcodes	Inline	0		7	1	0
bw	Expand to the logo for Bobbing Wide	1	oik	Inline	0		7	1	0
bw_autop	Dynamically re-enable/disable automatic paragraph generation	1	oik-css	Block	0		7	1	0
bw_blog	Select blog to process	1	oik-ms	Block	0		7	1	0
bw_blogs	List blogs or display content for selected blogs	1	oik-ms	Block	1		7	1	1
bw_codes	Display the currently available shortcodes	1	oik	Block	0		7	1	0
bw_contact	Primary contact name	1	oik	Inline	1		7	1	1
bw_directions	Display a 'Google directions' button.	1	oik	Block	1		7	1	1
bw_geo	Latitude and Longitude	1	oik	Block	0		7	1	0
bw_parent	Display a link back to the parent page	1	oik	Inline	1		7	1	1
bw_rwd	Dynamically generate oik responsive web design CSS classes	1	oik-rwd	Block	0		7	1	0
etag	End a tag started with [stag]	1	core	Inline	0		7	1	0
file	Display reference for a file	1	oik-shortcodes	Block	0		7	1	0
29608	trac_29608	0	core	Block	0		7	1	0
artisteer	Styled form of Artisteer	0	oik-bob-bing-wide	Inline	0		7	1	0
bp	Styled form of BuddyPress	0	oik-bob-bing-wide	Inline	0		7	1	0
bw_abbr	Format an abbreviation	0	oik	Inline	0		7	1	0
bw_acronym	Format an acronym	0	oik	Inline	0		7	1	0
bw_action	bw_shortcode_event	0	oik-bob-bing-wide	Mixed	0		7	1	0
bw_admin	Display the Admin contact name	0	oik	Mixed	0		7	1	0
bw_alt_slogan	Alternative slogan	0	oik	Block	0		7	1	0
bw_business	Display your Business name	0	oik	Block	1		7	1	1
bw_company	Company name	0	oik	Block	1		7	1	1
bw_crumbs	Display breadcrumbs	0	oik-bob-bing-wide	Block	0		7	1	0
bw_domain	Display the domain name	0	oik	Block	0		7	1	0
bw_eblock	end a [bw_block]	0	oik	Block	0		7	1	0
bw_editcss	Edit Custom CSS file button	0	oik	Block	0		7	1	0
bw_email_signature	Format the email signature	0	core	Block	0		7	1	0
bw_facebook	Facebook link	0	oik	Inline	1		7	1	1
bw_flickr	Flickr link	0	oik	Inline	1		7	1	1
bw_formal	Formal company name	0	oik	Block	1		7	1	1
bw_google	Google+ link	0	oik	Inline	1		7	1	1
bw_google_plus	Google+ link	0	oik	Inline	0		7	1	0
bw_google-plus	Google+ link	0	oik	Inline	0		7	1	0
bw_googleplus	Google+ link	0	oik	Inline	0		7	1	0
bw_instagram	Follow me on Instagram	0	oik	Inline	1		7	1	1
bw_linkedin	Follow me on LinkedIn	0	oik	Inline	1		7	1	1
bw_loginout	Display the Login or Logout link	0	oik	Mixed	1		7	1	1
bw_picasa	Follow me on Picasa	0	oik	Inline	0		7	1	0
bw_pinterest	Follow me on Pinterest	0	oik	Inline	1		7	1	1
bw_power	Powered by WordPress	0	oik	Block	0		7	1	0
bw_qv	bw_shortcode_event	0	core	Block	0		7	1	0
bw_register	Display a link to the Registration form	0	oik	Block	0		7	1	0
bw_rpt	bw_shortcode_event	0	oik-bob-bing-wide	Block	1		7	1	1
bw_search	Display search form	0	oik-bob-bing-wide	Block	0		7	1	0
bw_slogan	Primary slogan	0	oik	Block	0		7	1	0
bw_squeeze	bw_shortcode_event	0	oik-squeeze	Block	1		7	1	1
bw_text	bw_shortcode_event	0	oik-bob-bing-wide	Block	0		7	1	0
bw_twitter	Follow me on Twitter	0	oik	Inline	1		7	1	1
bw_wpadmin	Site: link to wp-admin	0	oik	Block	0		7	1	0
bw_youtube	Follow me on YouTube	0	oik	Inline	1		7	1	1
bwtroff	Force trace off	0	oik	Block	0		7	1	0
bwtron	Force trace on	0	oik	Block	0		7	1	0
clear	Clear divs	0	core	Block	0		7	1	0
drupal	bw_shortcode_event	0	oik-bob-bing-wide	Block	0		7	1	0
dumptag	trac_29608_shortcode_dumptag	0	core	Block	0		7	1	0
ediv	end a &lt;div&gt; with &lt;/div&gt;	0	core	Block	0		7	1	0
footer_home_link	genesis_footer_home_link_shortcode	0	core	Block	0		7	1	0
footer_site_title	genesis_footer_site_title_shortcode	0	core	Block	0		7	1	0
gpslides	Display a Slideshow Gallery Pro slideshow	0	oik	Block	0		7	1	0
hook	bw_shortcode_event	0	oik-shortcodes	Block	0		7	1	0
lartisteer	Link to Artisteer	0	oik-bob-bing-wide	Inline	0		7	1	0
lbp	Link to BuddyPress	0	oik-bob-bing-wide	Inline	0		7	1	0
lbw	Link to Bobbing Wide sites	0	oik	Inline	0		7	1	0
ldrupal	Link to drupal.org	0	oik-bob-bing-wide	Inline	0		7	1	0
loik	Link to [oik]-plugins	0	oik	Inline	0		7	1	0
lwp	Link to WordPress.org	0	oik-bob-bing-wide	Inline	0		7	1	0
lwpms	Link to WordPress Multi Site	0	oik-bob-bing-wide	Inline	0		7	1	0
md	Format Markdown	0	oik-shortcodes	Mixed	1		7	1	1
ngslideshow	NextGen gallery slideshow	0	core	Block	0		7	1	0
noautop	trac_29608_noautop	0	core	Block	0		7	1	0
OIK	Spells out the <span class="bw_oik"><abbr title="OIK Information Kit">oik</abbr></span> backronym	0	oik	Inline	0		7	1	0
oik	Expand to the logo for oik	0	oik	Inline	0		7	1	0
oik_edd_apikey	get API key form for EDD	0	oik-edd	Block	0		7	1	0
paragraph	trac_29608_shortcode_paragraph	0	core	Block	0		7	1	0
parsed_source	bw_shortcode_event	0	oik-shortcodes	Block	0		7	1	0
sediv	Start and end a div	0	core	Inline	0		7	1	0
wp	Display a styled form of WordPress.	0	oik-bob-bing-wide	Inline	1		7	1	1
wpms	Styled form of WordPress Multi Site	0	oik-bob-bing-wide	Inline	0		7	1	0

## Sites
				40.8571428571
WordPress version	Site	Plugins	Themes		Update	Test	Notes	Effort	Days
"4.9.4"	wordpress	229	108		0	1		1
"4.9.1"	wpms	108	40		0	1	WPMS	1
"4.9.1"	oikcom	94	23		0	1		1
"4.7.3"	oikplug	94	23		0	0		0
"4.7.3"	bwdesign	84	34		1	1		1.1428571429
"4.7.3"	wp47	84	32		0	0	Test oikcom	0
"4.9.1"	oikcouk	76	12		0	0		0
"4.8.2"	oikeu	71	17		1	1	WPMS	1.1428571429
"4.4"	rcwdcom	66	36		1	0		0.1428571429
"4.9.4"	.	64	24		0	1		1
"4.4.7"	wporg	64	13		0	0		0
"4.9.4"	hm	57	17		0	1		1
"4.8"	officialcaravan	54	8		1	1		1.1428571429
"5.0-alpha-42125-src"	src	52	14		0	0		0
"4.3.6"	hampshire-eft	49	17		0	0		0
"4.7.8"	bwcom	48	13		1	1		1.1428571429
"4.9.4"	cwiccer	45	3		0	1		1
"5.0-alpha-42125-src"	wp50	44	13		0	1		1
"4.8"	hallsgs	41	20		1	1		1.1428571429
"4.9.4"	szerelmey	40	4		0	0		0
"4.4.11"	rjduk	39	20		1	1		1.1428571429
"4.0"	hifianswers	39	3		0	0		0
"3.8.1"	ourlistenersclub	39	13		0	0		0
"3.5"	wp34	39	12		0	0		0
"4.3.1"	handmadestudios	38	10		1	1		1.1428571429
"4.0"	oobit	38	7		0	0		0
"4.6.1"	symondson	36	8		0	0		0
"4.8.1"	wp-a2z	35	13		1	1	WPMS	1.1428571429
"3.8.1"	rf	35	15		0	0		0
"3.3.1"	symondson_internetMarketing	34	2		0	0		0
"4.7.3"	susancowemiller	33	10		1	1	WPMS	1.1428571429
"4.4.11"	rjd	33	12		0	0		0
"3.9.1"	olc	33	12		0	0		0
"3.4.1"	hm1013	31	5		0	0		0
"4.3.1"	aumabs	30	15		0	0		0
"3.6"	wws	30	6		0	0		0
"4.9.4"	wp-pompey	28	6		0	1		1
"4.7.4"	wpit	28	9		0	0		0
"4.4.12"	rathmorefinancial	28	13		0	0		0
"3.6.1"	janecoomb	28	8		0	0		0
"4.4.2"	wp-a2z-v4.4.2	27	6		0	0		0
"3.8.1"	act	27	10		0	0		0
"4.7.5"	colours	26	6		0	0		0
"4.7.3"	cookie-cat	26	6		1	1		1.1428571429
"3.8.11"	rjd2	25	8		0	0		0
"3.5.1"	yellowbrand	25	5		0	0		0
"3.3.2"	hm0618	25	5		0	0		0
"4.9.2"	aldworth	24	8		0	1		1
"4.8.1"	lalucouk	24	2		1	1		1.1428571429
"4.7.8"	rngs	24	11		1	1		1.1428571429
"3.5.1"	wp35	23	5		0	0		0
"4.8.2"	owcs	22	1		1	1		1.1428571429
"4.8"	bigram	21	2		1	1		1.1428571429
"4.2.10"	survive	21	8		0	0		0
"3.5.1"	bettercorestrength	21	13		0	0		0
"4.5.3"	dws	20	6		0	0		0
"4.2.7"	therealc	20	9		0	0		0
"3.6"	hsoh	19	9		0	0		0
"3.3.2"	hosh	19	7		0	0		0
"4.9.1"	tags	18	5		1	1		1.1428571429
"4.7.2"	engarc	18	3		0	0		0
"3.4.2"	edw	18	9		0	0		0
"3.0.5"	fsp	18	10		0	0		0
"3.2.1"	hsoh_old	17	7		0	0		0
"4.2.2"	balancingbyart	16	10		1	1		1.1428571429
"4.1.4"	wholebeingwellbeing	16	9		1	1		1.1428571429
"3.3.1"	eft	16	13		0	0		0
"4.7"	wpml	15	0		0	0		0
"4.4.2"	coaching2inspire	14	9		1	1		1.1428571429
"3.3.1"	happystevehook	14	4		0	0		0
"4.2.2"	pretty	13	7		1	1		1.1428571429
"3.6.1"	lfd4u	13	10		0	0		0
"4.8"	broad-builders	12	2		1	1		1.1428571429
"3.4.1"	secrets	12	3		0	0		0
"3.3.1"	gtate	12	6		0	0		0
"3.0.3"	blogbbf	12	13		0	0		0
"3.4.2"	eedge1114	11	4		0	0		0
"4.1.1"	classic	10	8		1	1		1.1428571429
"3.3.1"	eedge1114b	10	4		0	0		0
"4.6.3"	solentro	9	5		1	1		1.1428571429
"4.6.1"	pwaep	9	6		0	0		0
"3.6.1"	bwcom-renamed	9	4		0	0		0
"3.6.1"	bwdevel	9	2		0	0		0
"3.4.1"	wp33	9	9		0	0		0
"3.3.1"	eedge	9	8		0	0		0
"4.9.1"	gdwifa	8	4		0	1		1
"4.7"	phpunit	8	1		1	1		1.1428571429
"3.0"	design	7	4		0	0		0
"4.9"	owzs-pro	6	2		0	1		1
"3.3.1"	jtth	6	11		0	0		0
"3.5"	eoci	5	4		1	1		1.1428571429
"4.9-alpha-40977"	build	3	8		0	0		0
"3.9"	andrea	3	5		0	0		0
"3.2.1"	wp321	3	2		0	0		0
"4.9"	owzs	2	2		1	1		1.1428571429
"4.0"	oik-plugins.uk	2	3		0	0		0
"3.0"	dealwithstress	2	3		0	0		0
"3.9-alpha"	svn	1	5		0	0		0
"3.8"	wp38	1	3		0	0		0
"3.7.1"	wp371	1	2		0	0		0
"4.9-RC2"	wpms-saved	0	0		0	0		0
"4.8"	achoired-taste	0	3		1	1		1.1428571429
"4.7.3"	oikcom-renamed	0	0		0	0		0
"4.7.1"	wp473	0	0		0	0		0
"4.6"	wp46	0	0		0	0		0
"4.6.1"	wpit4.6	0	0		0	0		0
"4.5.4"	bigram-renamed	0	6		0	0		0
"4.5.4-alpha-38000"	hm-pregit	0	0		0	0		0
NOWPC	okeffed
NOVER	#
NOVER	..
NOVER	.idea
NOVER	18/05/18
NOVER	Home - Rathmore financial_files
NOVER	Pandb
NOVER	WP-Parser-master
NOVER	anchorgo
NOVER	anchorgolfcom
NOVER	bobbingw
NOVER	bw
NOVER	bwarchive
NOVER	bwpcsupp
NOVER	bwts
NOVER	bwwdcouk
NOVER	caravan
NOVER	ccd
NOVER	cjgs
NOVER	classicc
NOVER	cookie-category
NOVER	customers
NOVER	denise
NOVER	deniseth
NOVER	dimcl
NOVER	downloads
NOVER	drupal-libraries
NOVER	drupal-modules
NOVER	dtib
NOVER	eie
NOVER	fabt
NOVER	findaballtees
NOVER	findabalti
NOVER	fionathomas
NOVER	fobbonghide
NOVER	foppapedretti
NOVER	funkygreen
NOVER	gdw
NOVER	gdwifa-couk
NOVER	gibberd
NOVER	git
NOVER	gkz
NOVER	gordontate
NOVER	gravity
NOVER	grippii
NOVER	harvest
NOVER	hcc
NOVER	heft
NOVER	hehall
NOVER	herb
NOVER	i-promote
NOVER	images
NOVER	insurance
NOVER	itconsultant
NOVER	janecoombsinfo
NOVER	japics
NOVER	jbr
NOVER	jimmy
NOVER	kamarklew
NOVER	kate
NOVER	laravel
NOVER	lazzari
NOVER	lcm
NOVER	lettings-inc
NOVER	lg
NOVER	logos
NOVER	loneworking
NOVER	ltcf
NOVER	marshall
NOVER	mdap
NOVER	mdt
NOVER	mountainview
NOVER	mrlc
NOVER	nivo-slider-v2.7.1
NOVER	nivo-slider-v3.1
NOVER	nivo-slider-v3.2
NOVER	oik
NOVER	oik-batchmove
NOVER	oik-css
NOVER	oik-nivo-slider_svn
NOVER	oik-plugins
NOVER	oik-privacy-policy_svn
NOVER	paap
NOVER	pathofbeing
NOVER	pcs
NOVER	penoyre
NOVER	phpDocumentor2
NOVER	phpLibraries
NOVER	phpMailer_v2.3
NOVER	phpMailer_v5.1
NOVER	phpMyAdmin
NOVER	phpMyAdmin-3.2.5
NOVER	phpMyAdmin-3.3.2-all-languages
NOVER	phpMyAdmin-4.6.6-english
NOVER	phpMyAdmin-4.7.6-all-languages
NOVER	phpMyAdmin4.2.11
NOVER	pkgs
NOVER	premier
NOVER	prettier
NOVER	prettyas
NOVER	prettyas_old
NOVER	problem-solving
NOVER	quickstart-basic
NOVER	rcbnb
NOVER	rcgc
NOVER	rchc
NOVER	rcorguk
NOVER	rcr
NOVER	rcroofing
NOVER	rctc
NOVER	react
NOVER	react-SB
NOVER	retirementcoach
NOVER	retirementmanager
NOVER	rmt
NOVER	sc2
NOVER	sc2-pregit
NOVER	simple_html_dom
NOVER	sitemap_gen-1.5
NOVER	susan
NOVER	susancowereiki
NOVER	svn_assets
NOVER	svn_plugins
NOVER	svn_tools
NOVER	td
NOVER	techsupport
NOVER	twenty-tens.com
NOVER	twentyte
NOVER	uk-tides_svn
NOVER	uploadify
NOVER	us-tides_svn
NOVER	wc-logs
NOVER	wc-rest
NOVER	webdesign
NOVER	wp-admin
NOVER	wp-content
NOVER	wp-includes
NOVER	wp-super-cache
NOVER	wp071
NOVER	wp292
NOVER	wp331
NOVER	wp39
NOVER	wpg
NOVER	wpgit
NOVER	wplang
NOVER	wplang-3.6
NOVER	wpmudev
NOVER	wwwcomp
NOVER	xdebug
NOVER	xmas
NOVER	yellow
NOVER	yogatherapy.me

## content
Content summary – pre-enablement					5.0%	5.2%		1.0%	88.9%
				2692	2785		531	47995	54003
	Post type					Posts
Site	Gutenberg	Media	Revisions	n/a	Classic	Total	Gutenberg	Media	Revisions	n/a	Classic	Total	Date
qw	2	1	1	9	5	18	127	39	280	45	4	495	12/03/18
qw/cwiccer	2	1	1	6	0	10	64	19	326	2	0	411	12/03/18
qw/oikcom	3	1	1	7	20	32	620	968	4170	103	11637	17498	12/03/18
qw/oikcouk	2	1	1	7	18	29	216	648	857	120	7869	9710	12/03/18
qw/oikeu
qw/src	2	1	1	5	1	10	98	19	518	20	1	656	13/03/18
qw/wordpress	2	1	1	4	36	44	904	547	5398	181	23304	30334	13/03/18
qw/wp-pompey	3	1	1	7	2	14	112	75	568	16	19	790	13/03/18
qw/wpms
qw/wp50	2	1	1	5	0	9	9	17	21	0	0	47	13/03/18
qw/hm	5	1	1	5	12	24	428	288	3408	32	14	4170	12/03/18
qw/officialcaravan
qw/oobit
qw/bwcom
qw/bwdesign					0					0
qw/tags	2	1	1	5	6	15	114	165	4512	12	5147	9950	13/03/18
				0					0
				0					0
				0					0
				0					0

Block	2692
Media	2785
n/a	531
Classic	47995

## plugins
				84
Type	Component	Count	Author	Third Party	Tests	Site	Test compatible?	Compatible?
plugins	hookr	1	@explodybits	1		bwdesign
plugins	user-photo	1	<a href="http://weston.ruter.net/">Weston Ruter</a>	1		wp35
plugins	wp-crontrol	1	<a href="http://www.scompt.com/">Edward Dale</a> & <a href="http://lud.icro.us/">John Blackbourn</a>	1		ourlistenersclub
plugins	efficient-related-posts	2	Aaron D. Campbell	1		hm0618
plugins	paypal-framework	1	Aaron D. Campbell	1		ourlistenersclub
plugins	remember-me-checked	1	Aaron Edwards (for Incsub)	1		wpms
plugins	simple-instagram	1	Aaron Speer	1		rcwdcom
plugins	contact-form	1	AdamGold	1		wpms
plugins	press-permit-core	2	Agapetry Creations LLC	1		hifianswers
plugins	tweet-old-post	1	Ajay Matharu	1		symondson
plugins	google-map-shortcode	1	Alain Gonzalez	1		yellowbrand
plugins	regenerate-thumbnails	8	Alex Mills (Viper007Bond)	1		bwdesign
plugins	wp-memory-usage	1	Alex Rabe	1		wp35
plugins	featured-video-plus	1	Alexander H√∂reth	1		szerelmey
plugins	woocommerce-call-for-price	1	Algoritmika Ltd	1		bwcom
plugins	woocommerce-jetpack	2	Algoritmika Ltd	1		owcs
plugins	simple-tags	1	Amaury BALMER	1		symondson_internetMarketing
plugins	five-star-rating	1	Andrew Alba	1		bwdesign
plugins	log-deprecated-notices	2	Andrew Nacin	1		.
plugins	tinymce-advanced	5	Andrew Ozz	1		bwdesign
plugins	toolbar-theme-switcher	1	Andrey "Rarst" Savchenko	1		.
plugins	commentluv	1	Andy Bailey	1		symondson_internetMarketing
plugins	commentluv-premium	1	Andy Bailey	1		symondson
plugins	share-and-follow	1	Andy Killen	1		symondson
plugins	shipping-awd	1	Andy_P (modified by Mantish to make it state based)	1		wp47
plugins	all-in-one-favicon	1	Arne Franken	1		wp47
plugins	wp-db-backup	1	Austin Matzko	1		symondson_internetMarketing
plugins	akismet	85	Automattic	1		.
plugins	developer	1	Automattic	1		.
plugins	jetpack	41	Automattic			aldworth
plugins	monster-widget	1	Automattic	1		oobit
plugins	push-syndication	1	Automattic	1		wp47
plugins	stats	1	Automattic	1		bwdesign
plugins	woocommerce	22	Automattic			.
plugins	woocommerce-gateway-paypal-express-checkout	2	Automattic	1		bwcom
plugins	vip-scanner	1	Automattic (Original code by Pross Otto42 and Thorsten Ott)	1		oobit
plugins	woocommerce-quantity-increment	2	Automattic WooThemes	1		owcs
plugins	master-slider	1	averta	1		colours
plugins	masterslider	1	averta	1		colours
plugins	recent-posts	2	Barry (Incsub)	1		rcwdcom
plugins	membership	6	Barry (Incsub) Cole (Incsub)	1		.
plugins	wp-geo	1	Ben Huson	1		wp-pompey
plugins	captcha	3	BestWebSoft	1		eedge
plugins	google-sitemap-plugin	2	BestWebSoft	1		rjd2
plugins	better-wp-security	1	Bit51.com	1		wp34
plugins	sociable	4	Blogplay	1		hm0618
plugins	powerpress	2	Blubrry	1		janecoomb
plugins	edd	1	Bobbing Wide Pippin Williamson	1		wpms
plugins	27918	1	bobbingwide	1		wordpress	0
plugins	allow-reinstalls	17	bobbingwide		1	aldworth	1
plugins	bbboing	20	bobbingwide			cwiccer	1
plugins	bigram	3	bobbingwide			bigram	1
plugins	bobbing	7	bobbingwide			oikcouk	0
plugins	bs8484	1	bobbingwide	1		wordpress	0
plugins	bw-types	3	bobbingwide	1		bwcom	1
plugins	bwdesign	2	bobbingwide			bwdesign	1
plugins	calyx	1	bobbingwide	1		officialcaravan	0
plugins	commentason	1	bobbingwide	1		wordpress	0
plugins	cookie-cat	46	bobbingwide		1	.	1
plugins	cookie-category	6	bobbingwide			cookie-cat	1
plugins	d62wp	7	bobbingwide			bigram	0
plugins	dinlo	6	bobbingwide		1	hm	0
plugins	diy-oik	16	bobbingwide			dws	1
plugins	drafts-for-friends	3	bobbingwide	1		.	0
plugins	dtib-review	2	bobbingwide	1		wordpress	1
plugins	dws	2	bobbingwide			dws	0
plugins	effort	1	bobbingwide	1		wordpress	0
plugins	epages	3	bobbingwide	1		eedge	0
plugins	foobar	8	bobbingwide	1		oikcom	0
plugins	genesis-footer-widgets	10	bobbingwide			bigram	1
plugins	genesistant	15	bobbingwide			bigram	1
plugins	get-ctrl-importer	3	bobbingwide	1		officialcaravan	0
plugins	kate	1	bobbingwide	1		wordpress	1
plugins	localmail	2	bobbingwide	1		hsoh_old	0
plugins	mbo	2	bobbingwide	1		aumabs	0
plugins	oik	87	bobbingwide		1	.	1
plugins	oik-a2z	9	bobbingwide		1	bigram	1
plugins	oik-adr	1	bobbingwide	1		wordpress	1
plugins	oik-ajax	11	bobbingwide			bigram	1
plugins	oik-batch	31	bobbingwide		1	.	1
plugins	oik-batchmove	19	bobbingwide			.	1
plugins	oik-bbpress	11	bobbingwide	1		cwiccer	1
plugins	oik-blogger-redirect	10	bobbingwide	1		bwcom	1
plugins	oik-bob-bing-wide	42	bobbingwide		1	.	1
plugins	oik-book	1	bobbingwide	1		oobit	1
plugins	oik-bp-signup-email	5	bobbingwide	1		.	0
plugins	oik-business	1	bobbingwide	1		wordpress	1
plugins	oik-bwtrace	63	bobbingwide		1	.	1
plugins	oik-cartcountry-shipping	1	bobbingwide	1		wordpress	0
plugins	oik-child-theme	1	bobbingwide	1		wordpress	0
plugins	oik-clone	21	bobbingwide			.	1
plugins	oik-clone-wxr	1	bobbingwide	1		wordpress	0
plugins	oik-cmb	1	bobbingwide	1	1	wp47	0
plugins	oik-cons	3	bobbingwide	1		hm	1
plugins	oik-cookie-law	1	bobbingwide	1		wordpress	0
plugins	oik-cookie-list	5	bobbingwide	1		oikcom	0
plugins	oik-css	40	bobbingwide		1	aldworth	1
plugins	oik-css3	2	bobbingwide	1		hm	0
plugins	oik-dates	10	bobbingwide			dws	1
plugins	oik-debug-filters	14	bobbingwide	1		.	0
plugins	oik-downloads	1	bobbingwide	1		wordpress	1
plugins	oik-dropcap	2	bobbingwide	1		phpunit	0
plugins	oik-edd	6	bobbingwide		1	oikcom	1
plugins	oik-email-signature	17	bobbingwide	1		.	1
plugins	oik-external-link-warning	12	bobbingwide			cwiccer	1
plugins	oik-fields	54	bobbingwide			.	1
plugins	oik-fum	15	bobbingwide			act	0
plugins	oik-header	11	bobbingwide	1		cwiccer	1
plugins	oik-html-importer	1	bobbingwide	1		wordpress	0
plugins	oik-html2markdown	1	bobbingwide	1		wordpress	0
plugins	oik-i18n	1	bobbingwide		1	wordpress	1
plugins	oik-infusionsoft	5	bobbingwide	1		oikcom	0
plugins	oik-intouchcrm	2	bobbingwide	1		rf	0
plugins	oik-lib	12	bobbingwide			bwcom	1
plugins	oik-libs	11	bobbingwide		1	hm	1
plugins	oik-media	5	bobbingwide			bigram	1
plugins	oik-members	4	bobbingwide	1		hifianswers	0
plugins	oik-money	1	bobbingwide	1		wordpress	0
plugins	oik-moreoptions	9	bobbingwide			cwiccer	1
plugins	oik-ms	18	bobbingwide			bwcom	1
plugins	oik-mshot	12	bobbingwide			bwcom	1
plugins	oik-nivo-slider	42	bobbingwide			.	1
plugins	oik-options	1	bobbingwide	1		wordpress	1
plugins	oik-payments	1	bobbingwide	1		wordpress	0
plugins	oik-pgs	1	bobbingwide	1		wordpress	0
plugins	oik-plugin-fields	4	bobbingwide			bwdesign	1
plugins	oik-plugins	17	bobbingwide			.	1
plugins	oik-popup	10	bobbingwide			aumabs	1
plugins	oik-post-type-support	11	bobbingwide			bwdesign	1
plugins	oik-presentation	6	bobbingwide	1		oikeu	1
plugins	oik-privacy-policy	53	bobbingwide			.	1
plugins	oik-pro	1	bobbingwide	1		wordpress	1
plugins	oik-rating	9	bobbingwide	1		aumabs	1
plugins	oik-read-more	10	bobbingwide			hm	1
plugins	oik-republish	2	bobbingwide	1		ourlistenersclub	0
plugins	oik-requests	5	bobbingwide	1		oikcom	1
plugins	oik-responsive-menu	11	bobbingwide	1		bwdesign	1
plugins	oik-rewrite	1	bobbingwide	1		wordpress	0
plugins	oik-rwd	37	bobbingwide			aldworth	1
plugins	oik-sc-help	20	bobbingwide		1	.	1
plugins	oik-select-menu	2	bobbingwide	1		cwiccer	0
plugins	oik-shortcodes	17	bobbingwide			.	1
plugins	oik-shortcodes-a2z	5	bobbingwide		1	bwdesign	1
plugins	oik-sidebar	8	bobbingwide	1		bwdesign	0
plugins	oik-sites	6	bobbingwide			.	1
plugins	oik-squeeze	18	bobbingwide			aumabs	1
plugins	oik-syndicate	1	bobbingwide	1		wordpress	0
plugins	oik-testimonials	20	bobbingwide			aumabs	1
plugins	oik-theme-fields	5	bobbingwide			bwcom	1
plugins	oik-themes	12	bobbingwide			bwcom	1
plugins	oik-thesis-featurebox	2	bobbingwide	1		symondson	0
plugins	oik-thugin	3	bobbingwide	1		oikcom	1
plugins	oik-tip	1	bobbingwide			wordpress	1
plugins	oik-todo	5	bobbingwide	1		oikcom	1
plugins	oik-tos	2	bobbingwide	1		bwcom	1
plugins	oik-tunes	10	bobbingwide	1		officialcaravan	1
plugins	oik-types	37	bobbingwide			.	1
plugins	oik-user	18	bobbingwide			cwiccer	1
plugins	oik-video	22	bobbingwide			aumabs	1
plugins	oik-weight-zone-shipping	9	bobbingwide		1	officialcaravan	1
plugins	oik-weight-zone-shipping-pro	13	bobbingwide			cwiccer	1
plugins	oik-weightcountry-shipping	16	bobbingwide			cwiccer	0
plugins	oik-weightcountry-shipping-pro	11	bobbingwide			handmadestudios	0
plugins	oik-widget-cache	4	bobbingwide			oikcom	1
plugins	oik-window-width	11	bobbingwide			aldworth	1
plugins	oik-woo	3	bobbingwide	1		wordpress	0
plugins	oik-working-feedback	6	bobbingwide	1		oikcom	0
plugins	oik-wzs-rates	6	bobbingwide			officialcaravan	1
plugins	oik-zip	1	bobbingwide			wordpress	1
plugins	olc	4	bobbingwide	1		hifianswers	0
plugins	oobar	2	bobbingwide			wordpress	1
plugins	play	3	bobbingwide	1	1	oikcouk	0
plugins	premium-plugins	1	bobbingwide	1		wordpress	1
plugins	restrict-shipping-classes	3	bobbingwide	1		src	0
plugins	rfi	3	bobbingwide	1		.	0
plugins	schunter	7	bobbingwide			.	0
plugins	setup	20	bobbingwide	1		.	0
plugins	slog	1	bobbingwide			wordpress	0
plugins	smart-bbboing	2	bobbingwide	1		rcwdcom	0
plugins	sneak-peek	4	bobbingwide	1		hampshire-eft	0
plugins	tags	3	bobbingwide			dws	0
plugins	tennis	1	bobbingwide	1		wordpress	0
plugins	trac29608	5	bobbingwide			.	0
plugins	txt2md	1	bobbingwide			wordpress	0
plugins	uk-tides	22	bobbingwide			bwcom	1
plugins	us-tides	11	bobbingwide			hm	1
plugins	wordpress-develop-tests	12	bobbingwide			hm	1
plugins	wpdb-alt	2	bobbingwide	1		oikcom	1
plugins	wppompey	3	bobbingwide	1		src	1
plugins	youtube_oembed_fix	1	bobbingwide	1		wp47	0
plugins	z	1	bobbingwide	1		wordpress	0
plugins	obsafe_print_r	5	bobbingwide	1		act	0
plugins	wp-clean-up	1	BoLiQuan	1		ourlistenersclub
plugins	Ultimate_VC_Addons	1	Brainstorm Force	1		colours
plugins	wp-slimstat	3	Camu	1		ourlistenersclub
plugins	car-demon	1	CarDemons	1		hallsgs
plugins	wp-members	15	Chad Butler	1		hifianswers
plugins	feedwordpress	1	Charles Johnson	1		.
plugins	cbnet-ping-optimizer	1	chipbennett	1		symondson_internetMarketing
plugins	wordpress-php-info	1	Christopher Ross	1		rjd
plugins	oa-social-login	1	Claude Schlesser	1		wp35
plugins	wpclef	2	Clef	1	1	colours
plugins	wpautoembed	2	Corey Wilson Jason Hines Christopher John Jackson	1		blogbbf
plugins	social	1	Crowd Favorite	1		yellowbrand
plugins	twitter-tools	2	Crowd Favorite	1		symondson_internetMarketing
plugins	plugin-activation-status	5	Curtiss Grymala	1		hampshire-eft
plugins	business-directory-plugin	1	D. Rodenbaugh	1		hifianswers
plugins	dd-formmailer	1	Dagon Design	1		symondson_internetMarketing
plugins	sitemap-generator	1	Dagon Design	1		symondson_internetMarketing
plugins	rewrite-rules-inspector	1	Daniel Bachhuber Automattic	1		oobit
plugins	username-changer	1	Daniel J Griffiths	1		rngs
plugins	woocommerce-add-countries	3	Daniele De Santis	1		oikeu
plugins	wp-optimize	3	David Anderson Ruhani Rabin Team Updraft	1		colours
plugins	genesis-layout-extras	1	David Decker - DECKERWEB	1		pretty
plugins	better-recent-posts-widget	1	David Gewirtz	1		szerelmey
plugins	mergebot	1	Delicious Brains	1		hm
plugins	wp-migrate-db	7	Delicious Brains	1		bwcom
plugins	private-buddypress	3	Dennis Morhardt	1		hosh
plugins	wp-maintenance-mode	1	Designmodo	1		colours
plugins	options-framework	1	Devin Price	1		szerelmey
plugins	revision-control	2	Dion Hulse	1		hampshire-eft
plugins	wp-performance-score-booster	1	Dipak C. Gajjar	1		engarc
plugins	public-post-preview	1	Dominik Schilling	1		wp47
plugins	cookies-for-comments	2	Donncha O Caoimh	1		janecoomb
plugins	exploit-scanner	1	Donncha O Caoimh	1		colours
plugins	backupbuddy	2	Dustin Bolton	1		symondson_internetMarketing
plugins	wordpress-security-lab	1	eConsultants.it Ltd	1		wp47
plugins	ecwid-shopping-cart	1	Ecwid Team	1		colours
plugins	dvteam	1	Egemenerd	1		szerelmey
plugins	divi-builder	1	Elegant Themes	1		src
plugins	acf	1	Elliot Condon	1		wpms
plugins	acf-options-page	1	Elliot Condon	1		szerelmey
plugins	acf-repeater	1	Elliot Condon	1		yellowbrand
plugins	logo-slider	1	EnigmaWeb	1		hallsgs
plugins	tubepress	1	Eric D. Hough	1		symondson_internetMarketing
plugins	search-and-replace	1	Frank B&uuml;ltge	1		symondson_internetMarketing
plugins	w3-total-cache	2	Frederick Townes	1		colours
plugins	shortcode-ui	3	Fusion Engineering and community	1		wordpress
plugins	simple-preview	1	Gabriel Nagmay	1		wp47
plugins	image-carousel	1	GhozyLab Inc.	1		broad-builders
plugins	wp-post-to-twitter	2	Glyn Mooney	1		hm0618
plugins	wp-customer-reviews	1	Go Web Solutions	1		rcwdcom
plugins	p3-profiler	3	GoDaddy.com	1		hifianswers
plugins	sf-author-url-control	1	Gr√©gory Viguier	1		wp34
plugins	extended-page-lists	6	grandslambert	1		act
plugins	go_portfolio	1	Granth	1		szerelmey
plugins	gtrans	1	GTranslate	1		rcwdcom
plugins	gutenberg	6	Gutenberg Team	1		cwiccer
plugins	appointments	2	Hakan Evin <hakan@incsub.com>	1		bettercorestrength
plugins	storm10	1	Herb	1		wordpress
plugins	oik-block	4	Herb Miller		1	hm
plugins	image-protector	1	Hirofumi Ohta	1		bettercorestrength
plugins	backupwordpress	30	Human Made Limited	1		aldworth
plugins	mailchimp-for-wp	2	ibericode	1		colours
plugins	bowe-codes	1	imath	1		.
plugins	backwpup	16	Inpsyde GmbH	1		.
plugins	groups	1	itthinx	1		wp47
plugins	woocommerce-volume-discount-coupons	2	itthinx	1		owcs
plugins	github-release-downloads	1	Ivan Ridao Freitas	1		.
plugins	mailchimp-widget	1	James Lafferty	1		coaching2inspire
plugins	broken-link-checker	6	Janis Elsts	1		janecoomb
plugins	wponlinebackup	3	Jason Woods @ Backup Technology	1		rjd
plugins	car-sales-pages	1	Jeff Bullins	1		hallsgs
plugins	ga-google-analytics	1	Jeff Starr	1		gdwifa
plugins	underconstruction	14	Jeremy Massel	1		classic
plugins	menu-exporter	2	Joe Hoyle - Human Made Limited	1		rjd
plugins	user-spam-remover	1	Joel Hardi	1		officialcaravan
plugins	limit-login-attempts	3	Johan Eenfeldt	1		colours
plugins	query-monitor	6	John Blackbourn	1	1	.
plugins	user-switching	1	John Blackbourn	1		oobit
plugins	voce-widget-cache	3	John Ciacia Mark Parolisi	1		oikcom
plugins	redirection	10	John Godley	1		bwdesign
plugins	post-type-switcher	16	John James Jacoby	1		aldworth
plugins	wp-term-images	1	John James Jacoby	1		hallsgs
plugins	simple-custom-css	1	John Regan Danny Van Kooten	1		szerelmey
plugins	widget-wrangler	7	Jonathan Daggerhart	1		blogbbf
plugins	media-file-renamer	5	Jordy Meow	1		aldworth
plugins	wp-to-twitter	5	Joseph Dolson	1		cookie-cat
plugins	members	2	Justin Tadlock	1		wp35
plugins	widget-output-cache	1	Kaspars Dambis	1		bwdesign
plugins	internal-link-manager	2	Kevin Leary	1		janecoomb
plugins	easy-privacy-policy	1	Kevin Sparrow	1		symondson_internetMarketing
plugins	googleanalytics	3	Kevin Sylvestre	1		rjd2
plugins	LayerSlider	1	Kreatura Media	1		aldworth
plugins	woocommerce-uk-counties	1	Lee Willis	1		wordpress
plugins	ltw-testimonials	11	LessThanWeb	1		act
plugins	WP-DraftsForFriends	2	Lester 'GaMerZ' Chan	1		.
plugins	wp-pagenavi	6	Lester 'GaMerZ' Chan	1		hifianswers
plugins	wp-polls	1	Lester 'GaMerZ' Chan	1		symondson_internetMarketing
plugins	wp-postviews	1	Lester 'GaMerZ' Chan	1		symondson_internetMarketing
plugins	wp-print	1	Lester 'GaMerZ' Chan	1		symondson_internetMarketing
plugins	duplicator	2	LifeInTheGrid	1		symondson_internetMarketing
plugins	site-icon-pro	1	Luca Spiller	1		szerelmey
plugins	quote-rotator	1	Luke Howell	1		jtth
plugins	wp-htaccess-editor	1	Lukenzi	1		engarc
plugins	mailchimp	1	MailChimp and Crowd Favorite	1		handmadestudios
plugins	multisite-cloner	3	Manuel Razzari Patricio Tarantino	1		oikeu
plugins	webchemistry-core	1	Mark Edmunds	1		rf
plugins	webchemistry-googleplugin	1	Mark Edmunds	1		rf
plugins	webchemistry-heatmap	1	Mark Edmunds	1		rf
plugins	webchemistry-searchenginesettings	1	Mark Edmunds	1		rf
plugins	webchemistry-seoboost	1	Mark Edmunds	1		rf
plugins	webchemistry-shortcodes	1	Mark Edmunds	1		rf
plugins	sitepush	1	Mark Rowatt Anderson	1		oobit
plugins	import-external-images	3	Marty Thornley	1		hifianswers
plugins	go-live-update-urls	4	Mat Lipe	1		dws
plugins	ml-slider	1	Matcha Labs	1		wpms
plugins	options-importer	4	Matthew Boynes	1		hampshire-eft
plugins	visual-form-builder	1	Matthew Muro	1		hifianswers
plugins	subscribe2	1	Matthew Robinson	1		yellowbrand
plugins	taxonomy-widget	1	Michael Fields	1		yellowbrand
plugins	taxonomy-images	1	Michael Fields Ben Huson	1		hallsgs
plugins	js_composer	2	Michael M - WPBakery.com	1		colours
plugins	maintenance-mode	2	Michael W√∂hrer	1		symondson_internetMarketing
plugins	add-to-any	9	micropat	1		act
plugins	si-contact-form	15	Mike Challis Ken Carlson	1		act
plugins	download-monitor	2	Mike Jolley	1		act
plugins	woocommerce-product-gift-wrap	2	Mike Jolley	1		owcs
plugins	wp-job-manager	1	Mike Jolley	1		rjd2
plugins	plugin-beta-tester	2	mitcho (Michael Yoshitaka Erlewine)	1		cwiccer
plugins	image-widget	2	Modern Tribe Inc.	1		symondson
plugins	the-events-calendar	8	Modern Tribe Inc.	1		act
plugins	sharebar	3	Monjurul Dolon	1		act
plugins	wp-statistics	2	Mostafa Soufi	1		janecoomb
plugins	vslider	1	Mr.Vibe	1		symondson
plugins	shortcake-ui-demo	1	Mte90	1		.
plugins	genesis-beta-tester	1	Nathan Rice	1		.
plugins	meta-tag-manager	1	NetWebLogic LLC	1		happystevehook
plugins	wp-car-manager	1	Never5	1		hallsgs
plugins	email-as-username-for-wp-members	1	New Tribes Mission (Stephen Narwold)	1		wp47
plugins	advanced-responsive-video-embedder	1	Nicolas Jonas	1		aumabs
plugins	shareadraft	1	Nikolay Bachiyski	1		wp47
plugins	post-types-order	1	Nsp Code	1		szerelmey
plugins	theme-check	1	Otto42 pross	1		cwiccer
plugins	welcome-pack	1	Paul Gibbs	1		wp-pompey
plugins	advanced-theme-switcher	1	Paul Menard (Incsub)	1		wpms
plugins	force-regenerate-thumbnails	4	Pedro Elsner	1		oikcom
plugins	timthumb-vulnerability-scanner	3	Peter Butler	1		rjd2
plugins	pc-searchengine-verify	11	Peter Coughlin	1		act
plugins	pinterest-verify	1	Phil Derksen	1		handmadestudios
plugins	bulk-taxonomy-edits	1	Phil Meadows	1		hifianswers
plugins	olc-tweaks	2	Phil Meadows	1		hifianswers
plugins	supplier-directory	2	Phil Meadows	1		hifianswers
plugins	quick-adsense	1	Philip Ze	1		symondson_internetMarketing
plugins	easy-nivo-slider	1	Phillip Bryan	1		symondson
plugins	easy-digital-downloads	10	Pippin Williamson and Company		1	.
plugins	popup-domination	2	PopUp Domination Team	1		.
plugins	qtranslate	2	Qian Qin	1		fsp
plugins	easy-fancybox	1	RavanH	1		.
plugins	portfolio-slideshow	6	Raygun	1		classic
plugins	revostock-gallery	1	RevoStock	1		bettercorestrength
plugins	cookie-law-info	2	Richard Ashby	1		szerelmey
plugins	frontend-uploader	1	Rinat Khaziev Daniel Bachhuber	1		bigram
plugins	pl-car-dealer	1	Roberto Bruno	1		hallsgs
plugins	gravityforms	12	rocketgenius	1		classic
plugins	soil	1	Roots	1		szerelmey
plugins	wp-video-lightbox	1	Ruhul Amin	1		oobit
plugins	slickr-flickr	1	Russell Jamieson	1		yellowbrand
plugins	WP-Parser	2	Ryan McCue Paul Gibbs Andrey "Rarst" Savchenko and Contributors	1		wordpress
plugins	exec-php	1	S&ouml;ren Weber	1		symondson_internetMarketing
plugins	s2member	3	s2Member / WebSharks Inc.	1		hifianswers
plugins	carousel-slider	1	Sayful Islam	1		hallsgs
plugins	audio	5	Scott Taylor	1		cwiccer
plugins	screets-lc	1	Screets Team	1		colours
plugins	plugin-dependencies	1	scribu	1		wordpress
plugins	ultimate-coming-soon-page	1	SeedProd	1		handmadestudios
plugins	wp-carousel-free	1	ShapedPlugin	1		hallsgs
plugins	shareaholic	2	Shareaholic	1		symondson
plugins	feed-footer	1	Sherief Mursyidi	1		symondson_internetMarketing
plugins	sg-cachepress	3	SiteGround	1		.
plugins	siteorigin-panels	4	SiteOrigin	1		bwdesign
plugins	so-widgets-bundle	3	SiteOrigin	1		cwiccer
plugins	youtube	1	Sonicity Plugins	1		design
plugins	wp-syntax	2	Steven A. Zahm	1		hm0618
plugins	widget-importer-exporter	5	Steven Gliebe	1		bwdesign
plugins	genesis-taxonomy-images	1	studiograsshopper themiked	1		hallsgs
plugins	genesis-connect-woocommerce	3	StudioPress	1		bwcom
plugins	genesis-responsive-slider	1	StudioPress	1		broad-builders
plugins	bulk-move	1	Sudar	1		ourlistenersclub
plugins	really-simple-captcha	1	Takayuki Miyoshi	1		officialcaravan
plugins	custom-contact-forms	1	Taylor Lovett	1		coaching2inspire
plugins	distributor	2	Taylor Lovett 10up	1	1	.
plugins	wp-seo	1	Team Yoast	1		pretty
plugins	bbpress	7	The bbPress Community	1		.
plugins	health-check	1	The WordPress.org community	1		wp47
plugins	fusion-builder	3	ThemeFusion	1		aldworth
plugins	fusion-core	3	ThemeFusion	1		aldworth
plugins	the-grid	1	Themeone	1		szerelmey
plugins	essential-grid	1	ThemePunch	1		colours
plugins	revslider	3	ThemePunch	1		aldworth
plugins	floating-admin-menu	1	Till Kr√ºss	1		oobit
plugins	all-in-one-event-calendar	4	Time.ly Network Inc.	1		hampshire-eft
plugins	megamenu	1	Tom Hemsley	1		handmadestudios
plugins	job-manager	2	Tom Townsend	1		rjd
plugins	tb-testimonials	7	Travis Ballard	1		hifianswers
plugins	one-click-child-theme	1	tychay	1		eft
plugins	woocommerce-poor-guys-swiss-knife	2	Uli Hake	1		owcs
plugins	export-users-to-csv	1	Ulrich Sossou	1		hifianswers
plugins	import-users-from-csv	4	Ulrich Sossou	1		act
plugins	ultimate-plugins-smart-update-pinger	1	Ultimate Plugins	1		symondson_internetMarketing
plugins	updraftplus	3	UpdraftPlus.Com DavidAnderson	1		act
plugins	easy-instagram	1	VeloMedia	1		rcwdcom
plugins	velvet-blues-update-urls	3	VelvetBlues.com	1		rjd
plugins	woocommerce-germanized	1	Vendidero	1		owcs
plugins	wp-simple-rss-feed-reader	1	Viancen	1		wws
plugins	twitter-tools-bitly-links	1	Viper007Bond	1		symondson_internetMarketing
plugins	user-role-editor	3	Vladimir Garagulya	1		rjd
plugins	custom-post-type-ui	2	WebDevStudios	1		szerelmey
plugins	page-list	1	webvitaly	1		szerelmey
plugins	really-simple-facebook-twitter-share-buttons	1	WhileTrue	1		symondson
plugins	simple-tweet	1	wokamoto	1		design
plugins	paypal-pro	1	WooThemes	1		wporg
plugins	woocommerce-colors	1	WooThemes	1		handmadestudios
plugins	woocommerce-smart-coupons	2	WooThemes	1		owcs
plugins	woosidebars	2	WooThemes	1		owcs
plugins	wordfence	6	Wordfence	1		engarc
plugins	link-manager	1	WordPress	1		wp35
plugins	classic-editor	5	WordPress Contributors	1		cwiccer
plugins	blogger-importer	3	wordpressdotorg	1		hm1013
plugins	debug-bar	5	wordpressdotorg	1		.
plugins	rss-importer	1	wordpressdotorg	1		officialcaravan
plugins	wordpress-importer	27	wordpressdotorg	1		.
plugins	wpcat2tag-importer	2	wordpressdotorg	1		bettercorestrength
plugins	auto-listings	1	WP Auto Listings	1		hallsgs
plugins	wcs-qr-code-generator	4	WP Code Snippets (Luke America)	1		bwdesign
plugins	wp-google-maps-gold	1	WP Google Maps	1		szerelmey
plugins	wp-google-maps-pro	1	WP Google Maps	1		szerelmey
plugins	wp-rocket	1	WP Media	1		szerelmey
plugins	wp-spamfree	2	WP-SpamFree	1		.
plugins	woocommerce-role-based-methods	2	WPBackOffice	1		owcs
plugins	cloner	1	WPMU DEV	1		wpms
plugins	multisite-content-copier	1	WPMU DEV	1		wpms
plugins	popover	2	WPMU DEV	1		rcwdcom
plugins	e-newsletter	1	WPMUDEV	1		wpms
plugins	contact-form-manager	1	xyzscripts.com	1		colours
plugins	aryo-activity-log	1	Yakir Sitbon Maor Chasen Ariel Klikstein	1		szerelmey
plugins	simple-drop-cap	1	Yudhistira Mauris	1		phpunit
plugins	jsforwp-blocks	2	Zac Gordon	1		src
plugins	debug-bar-cron	2	Zack Tollman Helen Hou-Sandi	1		bwdesign
Totals	1174	4009
themes	2014	1		1		wordpress
themes	2015	1		1		wordpress
themes	2016	1		1		wordpress
themes	__MACOSX	1		1		rjduk
themes	_oik	1		1		wordpress
plugins	.git	1		1		wordpress
plugins	.idea	4		1		.
themes	.idea	2		1		.
themes	act0331	1		1		rcwdcom
themes	act0402	1		1		act
themes	act0404	1		1		act
themes	act0408	1		1		act
themes	act0408a	1		1		act
themes	act1103	2		1		achoired-taste
plugins	actions	1		1		wpit
plugins	acurax-social-media-widget	2		1		janecoomb
plugins	adamrob-parallax-scroll	1		1		cwiccer
plugins	add-linked-images-to-gallery-v01	1		1		ourlistenersclub
plugins	add-paragraphs-option-to-text-widget	1		1		oikeu
plugins	admin	1		1		wordpress
plugins	advanced-custom-fields	4		1		hifianswers
plugins	advanced-custom-fields-fucked	1		1		yellowbrand
plugins	advanced-custom-fields-v4.3.9	1		1		wpms
themes	air-balloon-lite	1		1		bigram-renamed
plugins	Akismet-v3.1.8	1		1		hm
themes	aldworth	1		1		aldworth
themes	aldworth0628	1		1		aldworth
plugins	alexa-internet	2		1		janecoomb
plugins	all-in-one-event-calendar-effed	1		1		hampshire-eft
plugins	all-in-one-seo-pack	12		1		act
themes	altitude-pro	3		1		.
themes	alver0620	1		1		ourlistenersclub
themes	amazing-times	2		1		bwdesign
plugins	aqua-page-builder	1		1		wporg
themes	architecture	1		1		engarc
themes	architecture-v1-04	1		1		engarc
themes	Artisteer41	3		1		oikcom
themes	asteria-lite	1		1		wp47
themes	atahualpa	1		1		wholebeingwellbeing
themes	attitude	1		1		oikeu
themes	aumabs0402a	1		1		aumabs
themes	aumabs0402b	1		1		aumabs
themes	aumabs0403	1		1		aumabs
themes	aumabs0417	1		1		aumabs
themes	aumabs0425	2		1		aumabs
themes	aumabs0507	2		1		aumabs
themes	aumabs0507c	1		1		wordpress
themes	aumabs0520c	1		1		wordpress
plugins	Automattic-developer-57628b7	1		1		oobit
themes	Avada	1		1		aldworth
themes	aventurine	1		1		wpms
plugins	awd-weightcountry-shipping	3		1		handmadestudios
plugins	backup-qw	1		1		wordpress
plugins	backupbuddy.hold	1		1		szerelmey
plugins	backupcreator.hold	1		1		szerelmey
themes	bag2013	3		1		.
themes	bag2013-0616	1		1		wordpress
themes	bag2013-0626	1		1		wordpress
themes	bag2013-saved	1		1		wordpress
themes	bag2013-v0.1	2		1		rcwdcom
plugins	bainternet-posts-creation-limits	3		1		hifianswers
plugins	Basic-Auth-master	1		1		wp47
plugins	bb-plugin	2		1		src
themes	bba0605	1		1		balancingbyart
themes	bba0615	1		1		balancingbyart
themes	bba0622	1		1		balancingbyart
themes	bba0720c	2		1		balancingbyart
themes	bcs0313	1		1		bettercorestrength
themes	bcs0313c	1		1		bettercorestrength
plugins	beaver-builder-lite-version	1		1		cwiccer
themes	bg-mobile-first	2		1		bwdesign
plugins	bi2	1		1		ourlistenersclub
plugins	bigram-renamed	1		1		bigram
themes	blackbird	1		1		wp47
themes	blackbirdtheme-trial	1		1		wp47
themes	BlueMist	2		1		janecoomb
themes	boldy	1		1		wp34
plugins	botnet	1		1		wordpress
themes	bp-default	2		1		wp-pompey
themes	bp1027	1		1		wp33
themes	breakpoint	1		1		pwaep
themes	broad-builders	1		1		broad-builders
plugins	buddypress	6		1		.
plugins	BuddyPress	1		1	1	wp-pompey
plugins	bugrit	2		1		wordpress
themes	Builder-Cohen	1		1		hallsgs
themes	Builder-Madison	1		1		hallsgs
themes	Builder-Paige	1		1		hallsgs
themes	business-lite	1		1		wp34
plugins	bw-types-pregit	1		1		bwcom
themes	bw2013	4		1		bwcom
themes	bw20131004	2		1		bwcom
themes	bwblogwordpress	2		1		bwdesign
themes	bwdesign0622	1		1		bwdesign
themes	bwdesign0715	1		1		bwdesign
themes	bwdesign0830	1		1		bwdesign
themes	bwdesign0830c	1		1		bwdesign
themes	bwdesign1028	3		1		blogbbf
themes	bwdesign120209	1		1		wordpress
themes	bwdesign120209c	1		1		wordpress
themes	bwwow111120	1		1		wordpress
themes	bwwow1130	2		1		blogbbf
themes	bwwow1203	2		1		blogbbf
plugins	capability-manager-enhanced	2		1		hifianswers
plugins	cart66-lite	1		1		happystevehook
themes	cc0512	1		1		cookie-cat
themes	ccd1001	1		1		classic
themes	ccd1001c	1		1		classic
themes	centita	3		1		rjd
themes	centita3.0	2		1		rjd
themes	centita3.0-7	1		1		rjduk
themes	centita30c	2		1		rjd
themes	centita30c-7	1		1		rjduk
themes	cjw0118	2		1		coaching2inspire
themes	cjw1118	1		1		jtth
themes	cjw1123	1		1		jtth
themes	cjw1123c	1		1		jtth
themes	cjw1124	1		1		jtth
themes	cjw1128	1		1		jtth
themes	cjw1128c	1		1		jtth
themes	cjw20160315	2		1		coaching2inspire
themes	cjw20160316	1		1		coaching2inspire
themes	cjw20160316w	1		1		wordpress
themes	classic	5		1		blogbbf
plugins	cli	1		1		wordpress
plugins	climate	1		1		wordpress
plugins	CMB2	1		1	1	tags
plugins	cms-tree-page-view	5		1		bwdesign
plugins	collapsing-categories	3		1		hifianswers
plugins	colours2woo	1		1		wordpress
themes	constructzine-lite	1		1		aldworth
plugins	contact-form-7	6		1		aldworth
plugins	contus-video-gallery	1		1		bettercorestrength
plugins	cookie-batch	2		1		cookie-cat
plugins	cookie-category-pregit	1		1		cookie-cat
plugins	cookie-control	3		1		cookie-cat
plugins	cookie-opt-in	1		1		cwiccer
plugins	cool-timeline-pro	1		1		szerelmey
plugins	cornerstone	1		1		wpit
themes	Corporative	1		1		hm
themes	Corporative-child	1		1		hm
plugins	cron-view	2		1		bwdesign
plugins	css	2		1		src
themes	custom-community	1		1		aumabs
plugins	custom-content-type-manager	1		1	1	wpms
plugins	Custom-Meta-Boxes	2		1	1	bwdesign
plugins	custom-meta-widget	2		1		janecoomb
plugins	custom-metadata	1		1		wp47
plugins	custompress	1		1		wpms
themes	cwiccer1207	3		1		blogbbf
themes	DailyJournal	3		1		hifianswers
themes	dailyjournal-olc	3		1		hifianswers
themes	dailyjournal-olc2.3	1		1		olc
themes	DailyJournal2.3	2		1		olc
themes	DailyJournal2.4	1		1		ourlistenersclub
themes	default	5		1		blogbbf
themes	destro	1		1		bettercorestrength
plugins	developer-v1.0.0	1		1		oobit
plugins	dff	1		1		bwdesign
themes	diligent	1		1		bwdesign
plugins	directory	2		1		ourlistenersclub
themes	Divi	1		1		src
themes	dkret3	1		1		bettercorestrength
plugins	download-monitor-saved	1		1		act
plugins	dropcaps-shortcodes-and-widget	1		1		phpunit
themes	dtib0601	1		1		wpms
themes	dtib0601a	1		1		wpms
themes	dtib0723a	1		1		wpms
themes	dws	1				dealwithstress
themes	dws2016	2		1		dws
themes	dws2016-original	1		1		dws
themes	dwscomlaytfh	1		1		dws
plugins	easy-digital-downloads-free-download	1		1		act
plugins	easy-pricing-tables	1		1		.
themes	edge1117	1		1		eedge
themes	edge1117c	1		1		eedge
themes	edge1202	1		1		eedge
themes	edge120201	3		1		eedge
themes	edge120201c	3		1		eedge
themes	edge1202c	1		1		eedge
plugins	editorial-calendar	1		1		wp34
themes	edw0112	2		1		edw
themes	edw0114	1		1		edw
themes	edw0121	1		1		edw
themes	edw0125	1		1		edw
themes	edw0203	1		1		edw
themes	edw0616	1		1		edw
themes	edw0911	1		1		edw
plugins	eedge	4		1		eedge
themes	eft0621	2		1		eft
themes	eft0712	2		1		eft
themes	eft1009	2		1		eft
themes	eft1017	2		1		eft
themes	eft1018	2		1		eft
themes	eft1018r	2		1		eft
themes	eft121212	2		1		hampshire-eft
themes	eft20140523	1		1		hampshire-eft
themes	eft20140523-qw	1		1		hampshire-eft
themes	eft20140527	3		1		hampshire-eft
themes	eie120910	1		1		wp34
themes	eie120910c	2		1		wordpress
themes	elitist	1		1		.
themes	Engage	2		1		bwdesign
themes	eoci0112	3		1		eoci
themes	eps0906	1		1		rcwdcom
themes	etiquette-wp	1		1		wws
themes	fabt120330	1		1		rcwdcom
plugins	fancy-box	1		1		.
plugins	fancybox-for-wordpress	1		1		.
plugins	fatpanda-facebook-comments	1		1		symondson
themes	Feather	2		1		janecoomb
plugins	featured-content-gallery	1		1		symondson_internetMarketing
plugins	featured-image-widget	13		1		act
plugins	feed-them-social	1		1		handmadestudios
plugins	fff-cron-manager	1		1		ourlistenersclub
plugins	flagallery-skins	1		1		bettercorestrength
plugins	flash-album-gallery	1		1		bettercorestrength
plugins	follow-my-blog-post	2		1		janecoomb
plugins	foogallery-owl-carousel-template	1		1		hallsgs
themes	frantic	1		1		wp34
themes	freprotheme	1		1		bwdesign
themes	fsp0114	1		1		fsp
plugins	g-c-w	1		1		wordpress
plugins	g-pre-g	1		1		wordpress
plugins	gallery-widget	1		1		bwdesign
plugins	gcf	2		1		src
themes	gdwifa	1				gdwifa
themes	gdwifa20140303	2		1		gdwifa
themes	genesis	31				.
themes	genesis-2.1.3	1		1		.
themes	genesis-2.2.0	1		1		.
themes	genesis-2.2.3	1		1		wpms
themes	genesis-2.2.6	1		1		rjduk
themes	genesis-2.2.7	1		1		hallsgs
themes	genesis-a2z	4			1	bwdesign
themes	genesis-aati	1		1		wordpress
themes	genesis-broken	1		1		bwdesign
themes	genesis-bw	3				bwcom
themes	genesis-cc0512	1				cookie-cat
plugins	genesis-enews-extended	1		1		wholebeingwellbeing
themes	genesis-gdw	2		1		gdwifa
plugins	genesis-header-nav-develop	1		1		wordpress
themes	genesis-hehall	1				hallsgs
themes	genesis-hm	5				bwdesign
themes	genesis-hms	1		1		handmadestudios
themes	genesis-image	6			1	pretty
themes	genesis-image-pregit	1		1		wordpress
themes	genesis-odea	3		1		bwdesign
themes	genesis-oik	14			1	bwdesign
themes	genesis-paap	2		1		pretty
themes	genesis-sample	1		1		wholebeingwellbeing
themes	genesis-SB	3				bigram
themes	genesis-tags	2				tags
themes	genesis-v2.2.6	2		1		hm
plugins	genesis-variable-footer-widgets	1		1		.
themes	genesis-wbwb	1		1		wholebeingwellbeing
plugins	getver	1		1		wordpress
themes	gkz1116	1		1		rcwdcom
plugins	GlotPress-WP	1		1		wordpress
themes	goodtheme-lead	1		1		aumabs
plugins	google-analytics-for-wordpress	46		1		act
plugins	google-analytics-for-wordpress-renamed	1		1		hm
plugins	google-sitemap-generator	15		1		act
plugins	gravity-forms-custom-post-types	1		1		wpms
plugins	gravityformsmailchimp	1		1		yellowbrand
plugins	greprecated	4			1	bwcom
themes	gsph1103	1		1		blogbbf
themes	gta0422	1		1		gtate
themes	gta0614	1		1		gtate
themes	gta0621	1		1		gtate
themes	gta0722c	2		1		gtate
plugins	gutenberg-2.0.0	1		1		src
plugins	gutenberg-2.1.0	2		1		hm
plugins	gutenberg-2.3.0	2		1		hm
plugins	gutenberg-course	2		1		src
themes	heft0204	1		1		eft
themes	heft0205	2		1		eft
themes	heft1229	1		1		eft
themes	heft1229c	2		1		eft
themes	heft1229gc	1		1		eft
plugins	hello	2		1	1	wordpress
plugins	hello-dolly	5				oikeu
themes	hm120129	3		1		hm
themes	hm120206	4		1		hm
themes	hm120206c	4		1		hm
themes	hm140702	2		1		cwiccer
themes	hms0820	2		1		handmadestudios
themes	hms0826	2		1		handmadestudios
themes	hms0906	2		1		handmadestudios
themes	hms0907	2		1		handmadestudios
themes	hsoh0914	4		1		andrea
themes	hsoh0914a	4		1		andrea
themes	hsoh0922	4		1		hosh
themes	hsoh0922bp	1		1		wp33
themes	hsoh0928bp	3		1		hosh
themes	hsoh1015	1		1		wp33
themes	hsoh1027bp	4		1		hosh
plugins	html5-slideshow-presentations	1		1		oobit
plugins	hyperdb	1		1		oik-plugins.uk
plugins	image-store	1		1		fsp
themes	imbalance	1		1		rjduk
plugins	import-html-pages	1		1		wp35
plugins	import-users-from-csv-renamed	1		1		officialcaravan
themes	in-the-beginning	1		1		pwaep
plugins	inc	1		1		wp47
plugins	infolinks-officlial-plugin	1		1		symondson_internetMarketing
plugins	infusionsoft-web-tracker	1		1		symondson
themes	Innova	1		1		wp34
plugins	instagram-image-gallery	1		1		handmadestudios
themes	InterPhase	2		1		janecoomb
plugins	iphone-images	1		1		wordpress
plugins	issue-19	2		1		cwiccer
plugins	issue-49	1		1		wordpress
themes	japics1102	2		1		rcwdcom
plugins	jetpack-3.9.4	2		1		oikcom
plugins	jetpack-easy-playlists	1		1		officialcaravan
plugins	jetpack-extras	1		1		officialcaravan
plugins	jetpack-renamed	1		1	1	wp-a2z
themes	journal	2		1		bwdesign
plugins	jquery-featured-content-gallery	2		1		fsp
themes	jquery-UI	1		1		wordpress
themes	jquery-ui-1.12.1.custom	1		1		wordpress
themes	jquery-ui-themes-1.12.1	1		1		wordpress
plugins	json-rest-api	2		1		bwdesign
plugins	kiwi-logo-carousel	1		1		hallsgs
themes	lalu0915	1		1		lalucouk
themes	lalu1223	2		1		fsp
themes	li020226	1		1		rcwdcom
themes	lifestyle	1		1		symondson_internetMarketing
plugins	lightbox-plus	2		1		coaching2inspire
plugins	live-composer-page-builder	1		1		engarc
plugins	log-urgh	1		1		wordpress
plugins	logo-carousel	1		1		hallsgs
plugins	logo-carousel-slider	1		1		hallsgs
plugins	mad-mimi-broken	1		1		therealc
themes	Magnificent	1		1		lfd4u
themes	Martha	1		1		wporg
themes	Martha1	1		1		wporg
themes	match	1		1		wp47
themes	maximus	2		1		rathmorefinancial
themes	maximus-rf	2		1		rathmorefinancial
themes	mdt1209	1		1		rcwdcom
themes	minimalist-pro	2		1		bwdesign
themes	minn-lite	1		1		wpit
themes	modernbloggerpro	1		1		rjduk
plugins	more-privacy-options	3		1		rathmorefinancial
plugins	motors-car-dealership-classified-listings	1		1		hallsgs
plugins	mtouch-quiz	1		1		survive
plugins	multi-site-plugins-add-new	1		1		oikeu
plugins	my-page-order	1		1		yellowbrand
plugins	my-plugin	1		1	1	wordpress
plugins	my-wp-health-check	1		1		wp47
plugins	myplugins	1		1		wordpress
themes	mystile	1		1		wp47
plugins	network-privacy	6		1		bwcom
plugins	nextgen-gallery	13		1		balancingbyart
themes	nivo2011	5		1		oikeu
themes	nivoblackbird	1		1		wp47
themes	no-sidebar-pro	2		1		bwcom
themes	Nominal	1		1		pwaep
themes	novo	1		1		bwdesign
plugins	ns-cloner-site-copier	2		1		oikeu
themes	nuance-v1.2.3	1		1		bettercorestrength
themes	nuance-v1.2.4	1		1		wp47
plugins	OAuth1	1		1		wordpress
plugins	OAuth1-master	1		1		wp47
plugins	official-statcounter-plugin-for-wordpress	2		1		hosh
plugins	oik-2.5	1		1		rngs
plugins	oik-3.0.1	1		1		hallsgs
plugins	oik-3.0.2	1		1		wpit
plugins	oik-a2z-pregit	1		1		cwiccer
plugins	oik-api	1		1		wordpress
plugins	oik-batch-pre-resolving-cd-problem	2		1	1	src
plugins	oik-batch-pregit	1		1		oikeu
plugins	oik-batch-renamed	2		1		oikcom
plugins	oik-bbpress-ren	2		1		oikcom
plugins	oik-blogger-importer	3		1		hifianswers
plugins	oik-bob-bing-wide-1.21	1		1		.
plugins	oik-bob-bing-wide-1.30.2	1		1		bwdesign
plugins	oik-bwtrace-2.0.11	1		1		oikcouk
plugins	oik-bwtrace-2.0.12	1		1		wp47
plugins	oik-bwtrace-2.0.6	1		1		rngs
plugins	oik-bwtrace-git	1		1	1	bwcom
plugins	oik-bwtrace-ren	1		1		cookie-cat
plugins	oik-bwtrace-renamed	1		1		lalucouk
plugins	oik-bwtrace-too-new-for-oik-2.5	1		1		rcwdcom
plugins	oik-bwtrace-v2.0.11	1		1		officialcaravan
plugins	oik-bwtrace.2.0.11	1		1		bwdesign
plugins	oik-bwtrace.php	1		1		wordpress
plugins	oik-bwtracev2.0.12	1		1		wpms
plugins	oik-clone-20171114	2		1	1	oikcom
plugins	oik-content	2		1		symondson
plugins	oik-css-broken-1029	1		1		wordpress
plugins	oik-css-git-clone	2		1	1	oikcom
plugins	oik-css-pregit	2		1		aldworth
plugins	oik-edd-but-no-edd	1		1		cwiccer
plugins	oik-external-link-warning-pregit	1		1		wordpress
plugins	oik-f	1		1		wpms
plugins	oik-fields-1.36	1		1		.
plugins	oik-fields-pregit	1		1		hallsgs
plugins	oik-fields-ren	1		1		wpms
plugins	oik-fields-renamed	2		1		handmadestudios
plugins	oik-fields.x	1		1		bwdesign
plugins	oik-getimage	1		1		wordpress
plugins	oik-git-clone	1		1	1	hm
plugins	oik-jquery	1		1		wordpress
plugins	oik-l10n	1		1		wordpress
plugins	oik-mailchimp	1		1		wordpress
plugins	oik-make	1		1		wordpress
plugins	oik-ms-renamed	1		1		wpms
plugins	oik-nivo-slider-1.3	1		1		wpms
plugins	oik-nivo-slider-renamed	1		1		handmadestudios
plugins	oik-policies	1		1		wordpress
plugins	oik-popup-saved	1		1		bwdesign
plugins	oik-pregit	1		1		bwcom
plugins	oik-privacy-policy.php	1		1		wordpress
plugins	oik-ren	1		1		cookie-cat
plugins	oik-renamed	2		1		rjduk
plugins	oik-rwd-ren	1		1		wpms
plugins	oik-rwd-renamed	1		1		handmadestudios
plugins	oik-sc-help-1.9	1		1		.
plugins	oik-sc-help-renamed	1		1		wpms
plugins	oik-shutdown	1		1		wordpress
plugins	oik-signup-user-notification	1		1		wordpress
plugins	oik-squeeze-pregit	1		1		wordpress
plugins	oik-types-1.6	1		1		wpms
plugins	oik-types-pregit	1		1		officialcaravan
plugins	oik-types-renamed	1		1		handmadestudios
plugins	oik-types-v1.6	1		1		aumabs
plugins	oik-user-v0.5	1		1		wp47
plugins	oik-v2.6-alpha.0525	1		1		aumabs
plugins	oik-wcs-renamed	1		1		wporg
plugins	oik-weight-zone-shipping-pro-0.1.0	1		1		officialcaravan
plugins	oik-weight-zone-shipping-pro-v0.1.0	1		1		oikeu
plugins	oik-weight-zone-shipping-pro-v0.2.2	1		1		owzs-pro
plugins	oik-weightcountry-shipping-pro-v1.4.1	1		1		officialcaravan
plugins	oik-wzs-rates-pregit	1		1		wordpress
themes	oik0808	3		1		oikcom
themes	oik0819c	3		1		oikcom
themes	oik0917	1		1		wordpress
themes	oik0917c	1		1		wordpress
themes	oik0917r	1		1		wordpress
themes	oik0917s	1		1		wordpress
themes	oik0917t	4		1		oikcom
themes	oik0918	3		1		oikcom
themes	oik120206	1		1		wordpress
themes	oik120206c	1		1		wordpress
themes	oik120815	1		1		oikcouk
themes	oik2012	7		1		.
themes	oik20120	5		1		.
themes	oik310816	5		1		oikcom
themes	oik310816c	4		1		oikcom
themes	oik310816c-buggered	1		1		wordpress
themes	oik401126	1		1		wordpress
themes	oik401126-art4	1		1		wordpress
themes	oik410130	4		1		oikcom
themes	oik410130-1.1	2		1		oikcom
themes	oik410130c	4		1		oikcom
themes	oik410130c-1.1	2		1		oikcom
themes	oik410326	2		1		wordpress
themes	oik410923	4		1		oikcom
themes	oik410923c	1		1		wordpress
themes	oik420130	1		1		wordpress
themes	oik420130lm	1		1		wordpress
themes	oik420130wp	1		1		wordpress
themes	olc0618	2		1		olc
themes	olc120815	2		1		olc
themes	olc120815c	3		1		olc
themes	olc130611	1		1		wordpress
plugins	oldplay	2		1		wordpress
themes	omg	1		1		.
themes	one-pager-genesis-master	1		1		bwdesign
themes	oobit	6		1		oikeu
themes	oobit v1.0	1		1		rcwdcom
themes	oobit-extras	1		1		oobit
plugins	opcache	1		1		wordpress
plugins	owl-carousel	1		1		hallsgs
plugins	owzs-pro	1		1		wordpress
themes	p2	1		1		wp-pompey
plugins	page-tree	1		1		yellowbrand
themes	parallax-pro	5		1		bwcom
plugins	paypal-responder	1		1		ourlistenersclub
themes	pcs0809	1		1		rcwdcom
themes	pcs0822	1		1		rcwdcom
themes	pcs1003	1		1		rcwdcom
themes	pcs1013	1		1		jtth
themes	pcs20141209	1		1		wpms
themes	personaltrainer	2		1		aumabs
themes	phoenix0516	1		1		rcwdcom
plugins	php71-fixes	1		1	1	wordpress
plugins	php72-fixes	1		1	1	wordpress
plugins	phpunit	3		1	1	src
themes	pictorico	1		1		bigram-renamed
themes	pinboard	1		1		bettercorestrength
plugins	play-rel1	2		1		wordpress
plugins	play-rel2	2		1		wordpress
plugins	played	1		1		wp34
themes	pob1028	1		1		blogbbf
plugins	pods	2		1		wp47
plugins	popdom-themes-backup	1		1		.
plugins	PostMeta	1		1		wordpress
plugins	promotion-slider	1		1		aumabs
themes	psc0211	1		1		wordpress
themes	PureType	2		1		janecoomb
plugins	qtranslate-x	1		1		lalucouk
plugins	quick-pagepost-redirect-plugin	2		1		bwdesign
themes	rcgc0318	1		1		rcwdcom
themes	rcgc0818	1		1		rcwdcom
themes	rcr0725	2		1		rcwdcom
themes	rctc0130	2		1		rcwdcom
themes	rcwd0415	1		1		rcwdcom
plugins	recent-global-posts-widget	1		1		wpms
plugins	relocateme	1		1		wordpress
themes	responsive	1		1		janecoomb
plugins	rest-api	2		1		bigram
plugins	resume-submissions-job-postings	1		1		rjd2
themes	retro-fitted	1		1		lfd4u
themes	retro-fitted-child	1		1		lfd4u
themes	rf0122	1		1		.
themes	rf0202	2		1		rathmorefinancial
themes	rf0227	2		1		rathmorefinancial
themes	rf0227c	2		1		rathmorefinancial
themes	rf0311	5		1		rathmorefinancial
themes	rf0311c	4		1		rathmorefinancial
themes	rf0403	2		1		rathmorefinancial
themes	rf0403c	2		1		rathmorefinancial
themes	rf0510	2		1		rathmorefinancial
themes	rf0510c	3		1		cwiccer
plugins	rjd	1		1		rjduk
themes	rjdap	2		1		.
themes	rjdap-0.0.3	1		1		rjd
themes	rjdap-clone	1		1		rjd
themes	rjdpp	1		1		rjduk
themes	rmt4dws	1		1		dealwithstress
themes	rngs0414	3		1		rngs
themes	rngs0414c	3		1		rngs
themes	rngs0721	2		1		rngs
themes	rngs0721-ren	1		1		rngs
themes	rngs0721-wtf	1		1		rngs
themes	rngs0721c	2		1		rngs
themes	rngs0827	2		1		rngs
themes	rockstar	1		1		bettercorestrength
themes	royal	1		1		colours
plugins	s2member-files	4		1		cwiccer
plugins	s2member-logs	4		1		cwiccer
themes	s2s0515	2		1		rcwdcom
themes	s2s0515c	2		1		rcwdcom
plugins	sample	1		1		wordpress
plugins	saved_plugins	1		1		wpms
themes	sb0515	2		1		bigram-renamed
themes	sb1028	1		1		blogbbf
themes	sb2010	1		1		blogbbf
themes	sb2010_wm	1		1		blogbbf
themes	scr0909	3		1		hampshire-eft
themes	sds_2012	1		1		eoci
plugins	searchterms-tagging-2	2		1		janecoomb
plugins	seo-automatic-links	1		1		symondson_internetMarketing
plugins	sexybookmarks	8		1		act
plugins	sexybookmarks-broke	1		1		coaching2inspire
themes	sh0412	1		1		happystevehook
themes	sh0612	1		1		wp34
plugins	share-this	1		1		symondson_internetMarketing
plugins	shareadraft-master	1		1		wp47
themes	shell-lite	1		1		happystevehook
plugins	Shortcake	3		1		oikcom
plugins	shortcake-gutenberg	3		1		src
plugins	shortcode-reference	1		1		wpit
plugins	si-captcha-for-wordpress	11		1		.
plugins	simple-facebook-connect	6		1		blogbbf
plugins	simple-image-widget	2		1		eft
plugins	simple-twitter-connect	6		1		blogbbf
themes	simplest	1		1		.
themes	siteground-wp23	1		1		hallsgs
themes	siteground-wp63	1		1		hallsgs
themes	siteground-wp73	1		1		hallsgs
plugins	sitemap-redirect	1		1		wordpress
themes	sleekphoto	1		1		wpms
plugins	slide-in	1		1		wpms
plugins	slideshow-gallery-2	1		1		bwdesign
plugins	slideshow-gallery-pro	3		1		balancingbyart
plugins	slideshow-manager	1		1		wws
plugins	sliding-youtube-gallery	1		1		bettercorestrength
plugins	smart-google-code-inserter	1		1		aumabs
plugins	sociable-broken	1		1		therealc
themes	sol121012	2		1		solentro
themes	sol121012c	2		1		solentro
themes	sol150508	2		1		solentro
themes	sorbet	2		1		hampshire-eft
plugins	spam-destroyer	1		1		wp47
plugins	spam-reg-check	4		1		officialcaravan
themes	spartan	1		1		bettercorestrength
plugins	sql-csv	1		1		wordpress
themes	st0515	1		1		rcwdcom
themes	storefront	4		1		.
themes	style	1		1		wordpress
plugins	sub-page-summary	4		1		bwdesign
plugins	subpages-widget	1		1		yellowbrand
themes	superhero	1		1		hampshire-eft
themes	survive0310	4		1		bettercorestrength
themes	survive0310-art4	1		1		wordpress
themes	survive1120	2		1		wordpress
themes	survive1210	2		1		survive
themes	symondson0903	1		1		symondson
themes	symondson0903c	1		1		symondson
themes	szerelmey	1		1		szerelmey
themes	t10scom0201	1		1		wordpress
themes	t10scom120128	1		1		wordpress
themes	t40	1		1		wp47
plugins	test-41257	1		1	1	wordpress
plugins	testapi	1		1		wordpress
plugins	testimonials-by-woothemes	1		1		wp47
plugins	thank-me-later	1		1		symondson
themes	thematic	1		1		wordpress
themes	theme465	1		1		blogbbf
plugins	themes	1		1		wporg
themes	thesis_16	1		1		symondson
plugins	tides	1		1		wordpress
themes	tl0515	1		1		rcwdcom
plugins	transposh-translation-filter-for-wordpress	1		1		symondson_internetMarketing
themes	trcg120403	3		1		susancowemiller
themes	trcg120403c	3		1		susancowemiller
themes	trcg121026	1		1		wordpress
themes	Trim	2		1		janecoomb
themes	trtc0104	1		1		wordpress
themes	trtc0212	1		1		wordpress
themes	trtc0225	1		1		wordpress
themes	trtc0225c	1		1		wordpress
themes	trtc1230	1		1		wordpress
themes	twenty-seven-pro	2		1		bwdesign
themes	twentyeleven	57		1		.
themes	twentyeleven-2.1	1		1		wpms
themes	twentyfifteen	43		1		.
themes	twentyfifteen-v1.7	1		1		wp-a2z
themes	twentyfourteen	51		1		.
themes	twentyseventeen	26		1		.
themes	twentysixteen	23		1		.
themes	twentysixteen-symlinked-gitted	1		1		wp-a2z
themes	twentyten	56		1		.
themes	twentythirteen	53		1		.
themes	twentytwelve	57		1		.
plugins	twentytwelve-copied-from-theme	1		1		wordpress
plugins	u-buddypress-forum-editor	1		1		.
themes	uf-scribe	1		1		wpms
themes	uf-spirit	1		1		wpms
plugins	ultimate-tinymce	3		1		rjd
plugins	ultimate-tinymce-7	1		1		rjduk
themes	Universe	1		1		hallsgs
plugins	unserialize	1		1		wordpress
themes	Untitled	1		1		wordpress
themes	upfront	1		1		wpms
themes	vantage	2		1		oikeu
plugins	vc-extensions-bundle	1		1		szerelmey
plugins	visualizer	1		1		.
themes	wbwb20141021	2		1		wholebeingwellbeing
plugins	wc-call-for-price	1		1		bwcom
plugins	what-would-seth-godin-do	2		1		symondson
plugins	wmdum	1		1		lfd4u
themes	wonderflux	1		1		wp47
plugins	wonderplugin-carousel	1		1		broad-builders
plugins	wonderplugin-carousel-9.8	1		1		broad-builders
plugins	woocommerce-2.5.2	1		1		wp47
plugins	woocommerce-2.6	1		1		oikeu
plugins	woocommerce-2.6.12	1		1		officialcaravan
plugins	woocommerce-2.6.6	1		1		oikeu
plugins	woocommerce-3.0	1		1		oikeu
plugins	woocommerce-currency-switcher	1		1		wordpress
plugins	woocommerce-extra-charges-to-payment-gateways	2		1		owcs
plugins	woocommerce-multilingual	2		1		owcs
plugins	woocommerce-product-archive-customiser	1		1		handmadestudios
plugins	woocommerce-weight-country-based-shipping	1		1		wp47
plugins	woocommerce-wholesale-prices	2		1		owcs
plugins	woocommerce-wholesale-prices-premium	2		1		owcs
plugins	wordpress-beta-tester	6		1		hm
plugins	wordpress-custom-post-type-archive	1		1		yellowbrand
plugins	wordpress-develop-tests-svn-symlink	1		1		wordpress
plugins	WordPress-Importer	3		1	1	susancowemiller
plugins	wordpress-mu-domain-mapping	5				hosh
plugins	wordpress-mu-domain-mapping-disabled	1		1		hampshire-eft
plugins	wordpress-mu-domain-mapping-disabled-again	1		1		hampshire-eft
plugins	wordpress-mu-domain-mapping-local	1		1		rf
plugins	wordpress-mu-domain-mapping-qw	1		1		rathmorefinancial
plugins	wordpress-mu-domain-mapping-renamed	3		1		bwcom
plugins	wordpress-mu-domain-mapping-renamed-again	1		1		officialcaravan
plugins	wordpress-popup	1		1		hampshire-eft
plugins	wordpress-seo	66		1		.
plugins	wordpress-simple-survey	1		1		wp35
plugins	wordpress-social-login	2		1	1	officialcaravan
themes	workstation-pro	2		1		bwcom
themes	World	1		1		hallsgs
plugins	worldlogger-live-web-analytics	1		1		symondson_internetMarketing
plugins	wp-browscap	1		1		wordpress
plugins	wp-charts	2		1		.
plugins	wp-cli	5		1	1	oikcom
plugins	wp-custom-cssjs	1		1		szerelmey
plugins	wp-custom-taxonomy-meta	1		1		hallsgs
plugins	wp-db-backup-made	1		1		colours
plugins	wp-downloads	1		1		wordpress
plugins	wp-email-login	2		1		rngs
plugins	wp-google-maps	2		1		solentro
plugins	wp-mail-smtp	4		1		.
plugins	wp-migrate-db-0.9	1		1		wp-a2z
themes	wp-pompey	3		1		src
plugins	wp-responder-email-autoresponder-and-newsletter-plugin	1		1		symondson_internetMarketing
plugins	wp-seo-qtranslate-x	1		1		lalucouk
plugins	wp-simplemail	1		1		happystevehook
plugins	wp-smush-pro	1		1		wpms
plugins	wp-smushit	2		1		colours
plugins	wp-smushit.hold	1		1		szerelmey
plugins	wp-spamfree-7	1		1		rjduk
plugins	wp-super-cache	6		1		oikcom
plugins	wp-super-simple-speed	1		1		engarc
plugins	wp-top12	5			1	.
plugins	wpaudio-mp3-player	10		1		bwdesign
themes	wpg0216	4		1		.
themes	wpg0216bp	2		1		.
themes	wpg0216bp-renamed	1		1		wp-pompey
plugins	wpgmappity	1		1		yellowbrand
plugins	wpml-media	2		1		owcs
plugins	wpml-string-translation	2		1		owcs
plugins	wpml-translation-management	2		1		owcs
plugins	wpmu-dev-plusone	1		1		wpms
plugins	wpmudev-updates	6		1		.
themes	wporg-developer	1		1		wporg
plugins	wpremote	1		1	1	rcwdcom
plugins	WPRobot3	1		1		symondson_internetMarketing
plugins	wpseo-local	1		1		engarc
plugins	wysija-newsletters	4		1		tags
plugins	wysija-newsletters-norty	1		1		janecoomb
plugins	y	1		1		wordpress
themes	yellow0117	1		1		rcwdcom
themes	yellowbrand	1		1		yellowbrand
themes	yellowbrand-oik	1		1		yellowbrand
plugins	yith-woocommerce-wishlist	1		1		colours
plugins	youtube-embed-plus	1		1		bwdesign
plugins	zero_tolerance	1		1		symondson

## Components
Type	Component	Count	Author	Third Party	Tests	Test compatibility?	Compatible?
plugins	hookr	1	@explodybits	1
plugins	user-photo	1	<a href="http://weston.ruter.net/">Weston Ruter</a>	1
plugins	wp-crontrol	1	<a href="http://www.scompt.com/">Edward Dale</a> & <a href="http://lud.icro.us/">John Blackbourn</a>	1
plugins	efficient-related-posts	2	Aaron D. Campbell	1
plugins	paypal-framework	1	Aaron D. Campbell	1
plugins	remember-me-checked	1	Aaron Edwards (for Incsub)	1
plugins	simple-instagram	1	Aaron Speer	1
plugins	contact-form	1	AdamGold	1
plugins	press-permit-core	2	Agapetry Creations LLC	1
plugins	tweet-old-post	1	Ajay Matharu	1
plugins	google-map-shortcode	1	Alain Gonzalez	1
plugins	regenerate-thumbnails	8	Alex Mills (Viper007Bond)	1
plugins	wp-memory-usage	1	Alex Rabe	1
plugins	featured-video-plus	1	Alexander H√∂reth	1
plugins	woocommerce-call-for-price	1	Algoritmika Ltd	1
plugins	woocommerce-jetpack	2	Algoritmika Ltd	1
plugins	simple-tags	1	Amaury BALMER	1
plugins	five-star-rating	1	Andrew Alba	1
plugins	log-deprecated-notices	2	Andrew Nacin	1
plugins	tinymce-advanced	5	Andrew Ozz	1
plugins	toolbar-theme-switcher	1	Andrey "Rarst" Savchenko	1
plugins	commentluv	1	Andy Bailey	1
plugins	commentluv-premium	1	Andy Bailey	1
plugins	share-and-follow	1	Andy Killen	1
plugins	shipping-awd	1	Andy_P (modified by Mantish to make it state based)	1
plugins	all-in-one-favicon	1	Arne Franken	1
plugins	wp-db-backup	1	Austin Matzko	1
plugins	akismet	85	Automattic	1
plugins	developer	1	Automattic	1
plugins	jetpack	41	Automattic
plugins	monster-widget	1	Automattic	1
plugins	push-syndication	1	Automattic	1
plugins	stats	1	Automattic	1
plugins	woocommerce	22	Automattic
plugins	woocommerce-gateway-paypal-express-checkout	2	Automattic	1
plugins	vip-scanner	1	Automattic (Original code by Pross Otto42 and Thorsten Ott)	1
plugins	woocommerce-quantity-increment	2	Automattic WooThemes	1
plugins	master-slider	1	averta	1
plugins	masterslider	1	averta	1
plugins	recent-posts	2	Barry (Incsub)	1
plugins	membership	6	Barry (Incsub) Cole (Incsub)	1
plugins	wp-geo	1	Ben Huson	1
plugins	captcha	3	BestWebSoft	1
plugins	google-sitemap-plugin	2	BestWebSoft	1
plugins	better-wp-security	1	Bit51.com	1
plugins	sociable	4	Blogplay	1
plugins	powerpress	2	Blubrry	1
plugins	edd	1	Bobbing Wide Pippin Williamson	1
plugins	27918	1	bobbingwide	1
plugins	allow-reinstalls	17	bobbingwide		1	0	1
plugins	bbboing	20	bobbingwide			1
plugins	bigram	3	bobbingwide			0
plugins	bobbing	7	bobbingwide			0
plugins	bs8484	1	bobbingwide	1		0
plugins	bw-types	3	bobbingwide	1
plugins	bwdesign	2	bobbingwide
plugins	calyx	1	bobbingwide	1
plugins	commentason	1	bobbingwide	1
plugins	cookie-cat	46	bobbingwide		1
plugins	cookie-category	6	bobbingwide
plugins	d62wp	7	bobbingwide
plugins	dinlo	6	bobbingwide		1
plugins	diy-oik	16	bobbingwide
plugins	drafts-for-friends	3	bobbingwide	1
plugins	dtib-review	2	bobbingwide	1
plugins	dws	2	bobbingwide
plugins	effort	1	bobbingwide	1
plugins	epages	3	bobbingwide	1
plugins	foobar	8	bobbingwide	1
plugins	genesis-footer-widgets	10	bobbingwide
plugins	genesistant	15	bobbingwide
plugins	get-ctrl-importer	3	bobbingwide	1
plugins	kate	1	bobbingwide	1
plugins	localmail	2	bobbingwide	1
plugins	mbo	2	bobbingwide	1
plugins	oik	87	bobbingwide		1
plugins	oik-a2z	9	bobbingwide		1
plugins	oik-adr	1	bobbingwide	1
plugins	oik-ajax	11	bobbingwide
plugins	oik-batch	31	bobbingwide		1
plugins	oik-batchmove	19	bobbingwide
plugins	oik-bbpress	11	bobbingwide	1
plugins	oik-blogger-redirect	10	bobbingwide	1
plugins	oik-bob-bing-wide	42	bobbingwide		1
plugins	oik-book	1	bobbingwide	1
plugins	oik-bp-signup-email	5	bobbingwide	1
plugins	oik-business	1	bobbingwide	1
plugins	oik-bwtrace	63	bobbingwide		1
plugins	oik-cartcountry-shipping	1	bobbingwide	1
plugins	oik-child-theme	1	bobbingwide	1
plugins	oik-clone	21	bobbingwide
plugins	oik-clone-wxr	1	bobbingwide	1
plugins	oik-cmb	1	bobbingwide	1	1
plugins	oik-cons	3	bobbingwide	1
plugins	oik-cookie-law	1	bobbingwide	1
plugins	oik-cookie-list	5	bobbingwide	1
plugins	oik-css	40	bobbingwide		1
plugins	oik-css3	2	bobbingwide	1
plugins	oik-dates	10	bobbingwide
plugins	oik-debug-filters	14	bobbingwide	1
plugins	oik-downloads	1	bobbingwide	1
plugins	oik-dropcap	2	bobbingwide	1
plugins	oik-edd	6	bobbingwide		1
plugins	oik-email-signature	17	bobbingwide	1
plugins	oik-external-link-warning	12	bobbingwide
plugins	oik-fields	54	bobbingwide
plugins	oik-fum	15	bobbingwide
plugins	oik-header	11	bobbingwide	1
plugins	oik-html-importer	1	bobbingwide	1
plugins	oik-html2markdown	1	bobbingwide	1
plugins	oik-i18n	1	bobbingwide		1
plugins	oik-infusionsoft	5	bobbingwide	1
plugins	oik-intouchcrm	2	bobbingwide	1
plugins	oik-lib	12	bobbingwide
plugins	oik-libs	11	bobbingwide		1
plugins	oik-media	5	bobbingwide
plugins	oik-members	4	bobbingwide	1
plugins	oik-money	1	bobbingwide	1
plugins	oik-moreoptions	9	bobbingwide
plugins	oik-ms	18	bobbingwide
plugins	oik-mshot	12	bobbingwide
plugins	oik-nivo-slider	42	bobbingwide
plugins	oik-options	1	bobbingwide	1
plugins	oik-payments	1	bobbingwide	1
plugins	oik-pgs	1	bobbingwide	1
plugins	oik-plugin-fields	4	bobbingwide
plugins	oik-plugins	17	bobbingwide
plugins	oik-popup	10	bobbingwide
plugins	oik-post-type-support	11	bobbingwide
plugins	oik-presentation	6	bobbingwide	1
plugins	oik-privacy-policy	53	bobbingwide
plugins	oik-pro	1	bobbingwide	1
plugins	oik-rating	9	bobbingwide	1
plugins	oik-read-more	10	bobbingwide
plugins	oik-republish	2	bobbingwide	1
plugins	oik-requests	5	bobbingwide	1
plugins	oik-responsive-menu	11	bobbingwide	1
plugins	oik-rewrite	1	bobbingwide	1
plugins	oik-rwd	37	bobbingwide
plugins	oik-sc-help	20	bobbingwide		1
plugins	oik-select-menu	2	bobbingwide	1
plugins	oik-shortcodes	17	bobbingwide
plugins	oik-shortcodes-a2z	5	bobbingwide		1
plugins	oik-sidebar	8	bobbingwide	1
plugins	oik-sites	6	bobbingwide
plugins	oik-squeeze	18	bobbingwide
plugins	oik-syndicate	1	bobbingwide	1
plugins	oik-testimonials	20	bobbingwide
plugins	oik-theme-fields	5	bobbingwide
plugins	oik-themes	12	bobbingwide
plugins	oik-thesis-featurebox	2	bobbingwide	1
plugins	oik-thugin	3	bobbingwide	1
plugins	oik-tip	1	bobbingwide
plugins	oik-todo	5	bobbingwide	1
plugins	oik-tos	2	bobbingwide	1
plugins	oik-tunes	10	bobbingwide	1
plugins	oik-types	37	bobbingwide
plugins	oik-user	18	bobbingwide
plugins	oik-video	22	bobbingwide
plugins	oik-weight-zone-shipping	9	bobbingwide		1
plugins	oik-weight-zone-shipping-pro	13	bobbingwide
plugins	oik-weightcountry-shipping	16	bobbingwide
plugins	oik-weightcountry-shipping-pro	11	bobbingwide
plugins	oik-widget-cache	4	bobbingwide
plugins	oik-window-width	11	bobbingwide
plugins	oik-woo	3	bobbingwide	1
plugins	oik-working-feedback	6	bobbingwide	1
plugins	oik-wzs-rates	6	bobbingwide
plugins	oik-zip	1	bobbingwide
plugins	olc	4	bobbingwide	1
plugins	oobar	2	bobbingwide
plugins	play	3	bobbingwide	1	1
plugins	premium-plugins	1	bobbingwide	1
plugins	restrict-shipping-classes	3	bobbingwide	1
plugins	rfi	3	bobbingwide	1
plugins	schunter	7	bobbingwide
plugins	setup	20	bobbingwide	1
plugins	slog	1	bobbingwide
plugins	smart-bbboing	2	bobbingwide	1
plugins	sneak-peek	4	bobbingwide	1
plugins	tags	3	bobbingwide
plugins	tennis	1	bobbingwide	1
plugins	trac29608	5	bobbingwide
plugins	txt2md	1	bobbingwide
plugins	uk-tides	22	bobbingwide
plugins	us-tides	11	bobbingwide
plugins	wordpress-develop-tests	12	bobbingwide
plugins	wpdb-alt	2	bobbingwide	1
plugins	wppompey	3	bobbingwide	1
plugins	youtube_oembed_fix	1	bobbingwide	1
plugins	z	1	bobbingwide	1
plugins	obsafe_print_r	5	bobbingwide vsgloik	1
plugins	wp-clean-up	1	BoLiQuan	1
plugins	Ultimate_VC_Addons	1	Brainstorm Force	1
plugins	wp-slimstat	3	Camu	1
plugins	car-demon	1	CarDemons	1
plugins	wp-members	15	Chad Butler	1
plugins	feedwordpress	1	Charles Johnson	1
plugins	cbnet-ping-optimizer	1	chipbennett	1
plugins	wordpress-php-info	1	Christopher Ross	1
plugins	oa-social-login	1	Claude Schlesser	1
plugins	wpclef	2	Clef	1	1
plugins	wpautoembed	2	Corey Wilson Jason Hines Christopher John Jackson	1
plugins	social	1	Crowd Favorite	1
plugins	twitter-tools	2	Crowd Favorite	1
plugins	plugin-activation-status	5	Curtiss Grymala	1
plugins	business-directory-plugin	1	D. Rodenbaugh	1
plugins	dd-formmailer	1	Dagon Design	1
plugins	sitemap-generator	1	Dagon Design	1
plugins	rewrite-rules-inspector	1	Daniel Bachhuber Automattic	1
plugins	username-changer	1	Daniel J Griffiths	1
plugins	woocommerce-add-countries	3	Daniele De Santis	1
plugins	wp-optimize	3	David Anderson Ruhani Rabin Team Updraft	1
plugins	genesis-layout-extras	1	David Decker - DECKERWEB	1
plugins	better-recent-posts-widget	1	David Gewirtz	1
plugins	mergebot	1	Delicious Brains	1
plugins	wp-migrate-db	7	Delicious Brains	1
plugins	private-buddypress	3	Dennis Morhardt	1
plugins	wp-maintenance-mode	1	Designmodo	1
plugins	options-framework	1	Devin Price	1
plugins	revision-control	2	Dion Hulse	1
plugins	wp-performance-score-booster	1	Dipak C. Gajjar	1
plugins	public-post-preview	1	Dominik Schilling	1
plugins	cookies-for-comments	2	Donncha O Caoimh	1
plugins	exploit-scanner	1	Donncha O Caoimh	1
plugins	backupbuddy	2	Dustin Bolton	1
plugins	wordpress-security-lab	1	eConsultants.it Ltd	1
plugins	ecwid-shopping-cart	1	Ecwid Team	1
plugins	dvteam	1	Egemenerd	1
plugins	divi-builder	1	Elegant Themes	1
plugins	acf	1	Elliot Condon	1
plugins	acf-options-page	1	Elliot Condon	1
plugins	acf-repeater	1	Elliot Condon	1
plugins	logo-slider	1	EnigmaWeb	1
plugins	tubepress	1	Eric D. Hough	1
plugins	search-and-replace	1	Frank B&uuml;ltge	1
plugins	w3-total-cache	2	Frederick Townes	1
plugins	shortcode-ui	3	Fusion Engineering and community	1
plugins	simple-preview	1	Gabriel Nagmay	1
plugins	image-carousel	1	GhozyLab Inc.	1
plugins	wp-post-to-twitter	2	Glyn Mooney	1
plugins	wp-customer-reviews	1	Go Web Solutions	1
plugins	p3-profiler	3	GoDaddy.com	1
plugins	sf-author-url-control	1	Gr√©gory Viguier	1
plugins	extended-page-lists	6	grandslambert	1
plugins	go_portfolio	1	Granth	1
plugins	gtrans	1	GTranslate	1
plugins	gutenberg	6	Gutenberg Team	1
plugins	appointments	2	Hakan Evin <hakan@incsub.com>	1
plugins	storm10	1	Herb	1
plugins	oik-block	4	Herb Miller		1
plugins	image-protector	1	Hirofumi Ohta	1
plugins	backupwordpress	30	Human Made Limited	1
plugins	mailchimp-for-wp	2	ibericode	1
plugins	bowe-codes	1	imath	1
plugins	backwpup	16	Inpsyde GmbH	1
plugins	groups	1	itthinx	1
plugins	woocommerce-volume-discount-coupons	2	itthinx	1
plugins	github-release-downloads	1	Ivan Ridao Freitas	1
plugins	mailchimp-widget	1	James Lafferty	1
plugins	broken-link-checker	6	Janis Elsts	1
plugins	wponlinebackup	3	Jason Woods @ Backup Technology	1
plugins	car-sales-pages	1	Jeff Bullins	1
plugins	ga-google-analytics	1	Jeff Starr	1
plugins	underconstruction	14	Jeremy Massel	1
plugins	menu-exporter	2	Joe Hoyle - Human Made Limited	1
plugins	user-spam-remover	1	Joel Hardi	1
plugins	limit-login-attempts	3	Johan Eenfeldt	1
plugins	query-monitor	6	John Blackbourn	1	1
plugins	user-switching	1	John Blackbourn	1
plugins	voce-widget-cache	3	John Ciacia Mark Parolisi	1
plugins	redirection	10	John Godley	1
plugins	post-type-switcher	16	John James Jacoby	1
plugins	wp-term-images	1	John James Jacoby	1
plugins	simple-custom-css	1	John Regan Danny Van Kooten	1
plugins	widget-wrangler	7	Jonathan Daggerhart	1
plugins	media-file-renamer	5	Jordy Meow	1
plugins	wp-to-twitter	5	Joseph Dolson	1
plugins	members	2	Justin Tadlock	1
plugins	widget-output-cache	1	Kaspars Dambis	1
plugins	internal-link-manager	2	Kevin Leary	1
plugins	easy-privacy-policy	1	Kevin Sparrow	1
plugins	googleanalytics	3	Kevin Sylvestre	1
plugins	LayerSlider	1	Kreatura Media	1
plugins	woocommerce-uk-counties	1	Lee Willis	1
plugins	ltw-testimonials	11	LessThanWeb	1
plugins	WP-DraftsForFriends	2	Lester 'GaMerZ' Chan	1
plugins	wp-pagenavi	6	Lester 'GaMerZ' Chan	1
plugins	wp-polls	1	Lester 'GaMerZ' Chan	1
plugins	wp-postviews	1	Lester 'GaMerZ' Chan	1
plugins	wp-print	1	Lester 'GaMerZ' Chan	1
plugins	duplicator	2	LifeInTheGrid	1
plugins	site-icon-pro	1	Luca Spiller	1
plugins	quote-rotator	1	Luke Howell	1
plugins	wp-htaccess-editor	1	Lukenzi	1
plugins	mailchimp	1	MailChimp and Crowd Favorite	1
plugins	multisite-cloner	3	Manuel Razzari Patricio Tarantino	1
plugins	webchemistry-core	1	Mark Edmunds	1
plugins	webchemistry-googleplugin	1	Mark Edmunds	1
plugins	webchemistry-heatmap	1	Mark Edmunds	1
plugins	webchemistry-searchenginesettings	1	Mark Edmunds	1
plugins	webchemistry-seoboost	1	Mark Edmunds	1
plugins	webchemistry-shortcodes	1	Mark Edmunds	1
plugins	sitepush	1	Mark Rowatt Anderson	1
plugins	import-external-images	3	Marty Thornley	1
plugins	go-live-update-urls	4	Mat Lipe	1
plugins	ml-slider	1	Matcha Labs	1
plugins	options-importer	4	Matthew Boynes	1
plugins	visual-form-builder	1	Matthew Muro	1
plugins	subscribe2	1	Matthew Robinson	1
plugins	taxonomy-widget	1	Michael Fields	1
plugins	taxonomy-images	1	Michael Fields Ben Huson	1
plugins	js_composer	2	Michael M - WPBakery.com	1
plugins	maintenance-mode	2	Michael W√∂hrer	1
plugins	add-to-any	9	micropat	1
plugins	si-contact-form	15	Mike Challis Ken Carlson	1
plugins	download-monitor	2	Mike Jolley	1
plugins	woocommerce-product-gift-wrap	2	Mike Jolley	1
plugins	wp-job-manager	1	Mike Jolley	1
plugins	plugin-beta-tester	2	mitcho (Michael Yoshitaka Erlewine)	1
plugins	image-widget	2	Modern Tribe Inc.	1
plugins	the-events-calendar	8	Modern Tribe Inc.	1
plugins	sharebar	3	Monjurul Dolon	1
plugins	wp-statistics	2	Mostafa Soufi	1
plugins	vslider	1	Mr.Vibe	1
plugins	shortcake-ui-demo	1	Mte90	1
plugins	genesis-beta-tester	1	Nathan Rice	1
plugins	meta-tag-manager	1	NetWebLogic LLC	1
plugins	wp-car-manager	1	Never5	1
plugins	email-as-username-for-wp-members	1	New Tribes Mission (Stephen Narwold)	1
plugins	advanced-responsive-video-embedder	1	Nicolas Jonas	1
plugins	shareadraft	1	Nikolay Bachiyski	1
plugins	post-types-order	1	Nsp Code	1
plugins	theme-check	1	Otto42 pross	1
plugins	welcome-pack	1	Paul Gibbs	1
plugins	advanced-theme-switcher	1	Paul Menard (Incsub)	1
plugins	force-regenerate-thumbnails	4	Pedro Elsner	1
plugins	timthumb-vulnerability-scanner	3	Peter Butler	1
plugins	pc-searchengine-verify	11	Peter Coughlin	1
plugins	pinterest-verify	1	Phil Derksen	1
plugins	bulk-taxonomy-edits	1	Phil Meadows	1
plugins	olc-tweaks	2	Phil Meadows	1
plugins	supplier-directory	2	Phil Meadows	1
plugins	quick-adsense	1	Philip Ze	1
plugins	easy-nivo-slider	1	Phillip Bryan	1
plugins	easy-digital-downloads	10	Pippin Williamson and Company		1
plugins	popup-domination	2	PopUp Domination Team	1
plugins	qtranslate	2	Qian Qin	1
plugins	easy-fancybox	1	RavanH	1
plugins	portfolio-slideshow	6	Raygun	1
plugins	revostock-gallery	1	RevoStock	1
plugins	cookie-law-info	2	Richard Ashby	1
plugins	frontend-uploader	1	Rinat Khaziev Daniel Bachhuber	1
plugins	pl-car-dealer	1	Roberto Bruno	1
plugins	gravityforms	12	rocketgenius	1
plugins	soil	1	Roots	1
plugins	wp-video-lightbox	1	Ruhul Amin	1
plugins	slickr-flickr	1	Russell Jamieson	1
plugins	WP-Parser	2	Ryan McCue Paul Gibbs Andrey "Rarst" Savchenko and Contributors	1
plugins	exec-php	1	S&ouml;ren Weber	1
plugins	s2member	3	s2Member / WebSharks Inc.	1
plugins	carousel-slider	1	Sayful Islam	1
plugins	audio	5	Scott Taylor	1
plugins	screets-lc	1	Screets Team	1
plugins	plugin-dependencies	1	scribu	1
plugins	ultimate-coming-soon-page	1	SeedProd	1
plugins	wp-carousel-free	1	ShapedPlugin	1
plugins	shareaholic	2	Shareaholic	1
plugins	feed-footer	1	Sherief Mursyidi	1
plugins	sg-cachepress	3	SiteGround	1
plugins	siteorigin-panels	4	SiteOrigin	1
plugins	so-widgets-bundle	3	SiteOrigin	1
plugins	youtube	1	Sonicity Plugins	1
plugins	wp-syntax	2	Steven A. Zahm	1
plugins	widget-importer-exporter	5	Steven Gliebe	1
plugins	genesis-taxonomy-images	1	studiograsshopper themiked	1
plugins	genesis-connect-woocommerce	3	StudioPress	1
plugins	genesis-responsive-slider	1	StudioPress	1
plugins	bulk-move	1	Sudar	1
plugins	really-simple-captcha	1	Takayuki Miyoshi	1
plugins	custom-contact-forms	1	Taylor Lovett	1
plugins	distributor	2	Taylor Lovett 10up	1	1
plugins	wp-seo	1	Team Yoast	1
plugins	bbpress	7	The bbPress Community	1
plugins	health-check	1	The WordPress.org community	1
plugins	fusion-builder	3	ThemeFusion	1
plugins	fusion-core	3	ThemeFusion	1
plugins	the-grid	1	Themeone	1
plugins	essential-grid	1	ThemePunch	1
plugins	revslider	3	ThemePunch	1
plugins	floating-admin-menu	1	Till Kr√ºss	1
plugins	all-in-one-event-calendar	4	Time.ly Network Inc.	1
plugins	megamenu	1	Tom Hemsley	1
plugins	job-manager	2	Tom Townsend	1
plugins	tb-testimonials	7	Travis Ballard	1
plugins	one-click-child-theme	1	tychay	1
plugins	woocommerce-poor-guys-swiss-knife	2	Uli Hake	1
plugins	export-users-to-csv	1	Ulrich Sossou	1
plugins	import-users-from-csv	4	Ulrich Sossou	1
plugins	ultimate-plugins-smart-update-pinger	1	Ultimate Plugins	1
plugins	updraftplus	3	UpdraftPlus.Com DavidAnderson	1
plugins	easy-instagram	1	VeloMedia	1
plugins	velvet-blues-update-urls	3	VelvetBlues.com	1
plugins	woocommerce-germanized	1	Vendidero	1
plugins	wp-simple-rss-feed-reader	1	Viancen	1
plugins	twitter-tools-bitly-links	1	Viper007Bond	1
plugins	user-role-editor	3	Vladimir Garagulya	1
plugins	custom-post-type-ui	2	WebDevStudios	1
plugins	page-list	1	webvitaly	1
plugins	really-simple-facebook-twitter-share-buttons	1	WhileTrue	1
plugins	simple-tweet	1	wokamoto	1
plugins	paypal-pro	1	WooThemes	1
plugins	woocommerce-colors	1	WooThemes	1
plugins	woocommerce-smart-coupons	2	WooThemes	1
plugins	woosidebars	2	WooThemes	1
plugins	wordfence	6	Wordfence	1
plugins	link-manager	1	WordPress	1
plugins	classic-editor	5	WordPress Contributors	1
plugins	blogger-importer	3	wordpressdotorg	1
plugins	debug-bar	5	wordpressdotorg	1
plugins	rss-importer	1	wordpressdotorg	1
plugins	wordpress-importer	27	wordpressdotorg	1
plugins	wpcat2tag-importer	2	wordpressdotorg	1
plugins	auto-listings	1	WP Auto Listings	1
plugins	wcs-qr-code-generator	4	WP Code Snippets (Luke America)	1
plugins	wp-google-maps-gold	1	WP Google Maps	1
plugins	wp-google-maps-pro	1	WP Google Maps	1
plugins	wp-rocket	1	WP Media	1
plugins	wp-spamfree	2	WP-SpamFree	1
plugins	woocommerce-role-based-methods	2	WPBackOffice	1
plugins	cloner	1	WPMU DEV	1
plugins	multisite-content-copier	1	WPMU DEV	1
plugins	popover	2	WPMU DEV	1
plugins	e-newsletter	1	WPMUDEV	1
plugins	contact-form-manager	1	xyzscripts.com	1
plugins	aryo-activity-log	1	Yakir Sitbon Maor Chasen Ariel Klikstein	1
plugins	simple-drop-cap	1	Yudhistira Mauris	1
plugins	jsforwp-blocks	2	Zac Gordon	1
plugins	debug-bar-cron	2	Zack Tollman Helen Hou-Sandi	1
Totals	1174	4009
themes	2014	1		1
themes	2015	1		1
themes	2016	1		1
themes	__MACOSX	1		1
themes	_oik	1		1
plugins	.git	1		1
plugins	.idea	4		1
themes	.idea	2		1
themes	act0331	1		1
themes	act0402	1		1
themes	act0404	1		1
themes	act0408	1		1
themes	act0408a	1		1
themes	act1103	2		1
plugins	actions	1		1
plugins	acurax-social-media-widget	2		1
plugins	adamrob-parallax-scroll	1		1
plugins	add-linked-images-to-gallery-v01	1		1
plugins	add-paragraphs-option-to-text-widget	1		1
plugins	admin	1		1
plugins	advanced-custom-fields	4		1
plugins	advanced-custom-fields-fucked	1		1
plugins	advanced-custom-fields-v4.3.9	1		1
themes	air-balloon-lite	1		1
plugins	Akismet-v3.1.8	1		1
themes	aldworth	1		1
themes	aldworth0628	1		1
plugins	alexa-internet	2		1
plugins	all-in-one-event-calendar-effed	1		1
plugins	all-in-one-seo-pack	12		1
themes	altitude-pro	3		1
themes	alver0620	1		1
themes	amazing-times	2		1
plugins	aqua-page-builder	1		1
themes	architecture	1		1
themes	architecture-v1-04	1		1
themes	Artisteer41	3		1
themes	asteria-lite	1		1
themes	atahualpa	1		1
themes	attitude	1		1
themes	aumabs0402a	1		1
themes	aumabs0402b	1		1
themes	aumabs0403	1		1
themes	aumabs0417	1		1
themes	aumabs0425	2		1
themes	aumabs0507	2		1
themes	aumabs0507c	1		1
themes	aumabs0520c	1		1
plugins	Automattic-developer-57628b7	1		1
themes	Avada	1		1
themes	aventurine	1		1
plugins	awd-weightcountry-shipping	3		1
plugins	backup-qw	1		1
plugins	backupbuddy.hold	1		1
plugins	backupcreator.hold	1		1
themes	bag2013	3		1
themes	bag2013-0616	1		1
themes	bag2013-0626	1		1
themes	bag2013-saved	1		1
themes	bag2013-v0.1	2		1
plugins	bainternet-posts-creation-limits	3		1
plugins	Basic-Auth-master	1		1
plugins	bb-plugin	2		1
themes	bba0605	1		1
themes	bba0615	1		1
themes	bba0622	1		1
themes	bba0720c	2		1
themes	bcs0313	1		1
themes	bcs0313c	1		1
plugins	beaver-builder-lite-version	1		1
themes	bg-mobile-first	2		1
plugins	bi2	1		1
plugins	bigram-renamed	1		1
themes	blackbird	1		1
themes	blackbirdtheme-trial	1		1
themes	BlueMist	2		1
themes	boldy	1		1
plugins	botnet	1		1
themes	bp-default	2		1
themes	bp1027	1		1
themes	breakpoint	1		1
themes	broad-builders	1		1
plugins	buddypress	6		1
plugins	BuddyPress	1		1	1
plugins	bugrit	2		1
themes	Builder-Cohen	1		1
themes	Builder-Madison	1		1
themes	Builder-Paige	1		1
themes	business-lite	1		1
plugins	bw-types-pregit	1		1
themes	bw2013	4		1
themes	bw20131004	2		1
themes	bwblogwordpress	2		1
themes	bwdesign0622	1		1
themes	bwdesign0715	1		1
themes	bwdesign0830	1		1
themes	bwdesign0830c	1		1
themes	bwdesign1028	3		1
themes	bwdesign120209	1		1
themes	bwdesign120209c	1		1
themes	bwwow111120	1		1
themes	bwwow1130	2		1
themes	bwwow1203	2		1
plugins	capability-manager-enhanced	2		1
plugins	cart66-lite	1		1
themes	cc0512	1		1
themes	ccd1001	1		1
themes	ccd1001c	1		1
themes	centita	3		1
themes	centita3.0	2		1
themes	centita3.0-7	1		1
themes	centita30c	2		1
themes	centita30c-7	1		1
themes	cjw0118	2		1
themes	cjw1118	1		1
themes	cjw1123	1		1
themes	cjw1123c	1		1
themes	cjw1124	1		1
themes	cjw1128	1		1
themes	cjw1128c	1		1
themes	cjw20160315	2		1
themes	cjw20160316	1		1
themes	cjw20160316w	1		1
themes	classic	5		1
plugins	cli	1		1
plugins	climate	1		1
plugins	CMB2	1		1	1
plugins	cms-tree-page-view	5		1
plugins	collapsing-categories	3		1
plugins	colours2woo	1		1
themes	constructzine-lite	1		1
plugins	contact-form-7	6		1
plugins	contus-video-gallery	1		1
plugins	cookie-batch	2		1
plugins	cookie-category-pregit	1		1
plugins	cookie-control	3		1
plugins	cookie-opt-in	1		1
plugins	cool-timeline-pro	1		1
plugins	cornerstone	1		1
themes	Corporative	1		1
themes	Corporative-child	1		1
plugins	cron-view	2		1
plugins	css	2		1
themes	custom-community	1		1
plugins	custom-content-type-manager	1		1	1
plugins	Custom-Meta-Boxes	2		1	1
plugins	custom-meta-widget	2		1
plugins	custom-metadata	1		1
plugins	custompress	1		1
themes	cwiccer1207	3		1
themes	DailyJournal	3		1
themes	dailyjournal-olc	3		1
themes	dailyjournal-olc2.3	1		1
themes	DailyJournal2.3	2		1
themes	DailyJournal2.4	1		1
themes	default	5		1
themes	destro	1		1
plugins	developer-v1.0.0	1		1
plugins	dff	1		1
themes	diligent	1		1
plugins	directory	2		1
themes	Divi	1		1
themes	dkret3	1		1
plugins	download-monitor-saved	1		1
plugins	dropcaps-shortcodes-and-widget	1		1
themes	dtib0601	1		1
themes	dtib0601a	1		1
themes	dtib0723a	1		1
themes	dws	1
themes	dws2016	2		1
themes	dws2016-original	1		1
themes	dwscomlaytfh	1		1
plugins	easy-digital-downloads-free-download	1		1
plugins	easy-pricing-tables	1		1
themes	edge1117	1		1
themes	edge1117c	1		1
themes	edge1202	1		1
themes	edge120201	3		1
themes	edge120201c	3		1
themes	edge1202c	1		1
plugins	editorial-calendar	1		1
themes	edw0112	2		1
themes	edw0114	1		1
themes	edw0121	1		1
themes	edw0125	1		1
themes	edw0203	1		1
themes	edw0616	1		1
themes	edw0911	1		1
plugins	eedge	4		1
themes	eft0621	2		1
themes	eft0712	2		1
themes	eft1009	2		1
themes	eft1017	2		1
themes	eft1018	2		1
themes	eft1018r	2		1
themes	eft121212	2		1
themes	eft20140523	1		1
themes	eft20140523-qw	1		1
themes	eft20140527	3		1
themes	eie120910	1		1
themes	eie120910c	2		1
themes	elitist	1		1
themes	Engage	2		1
themes	eoci0112	3		1
themes	eps0906	1		1
themes	etiquette-wp	1		1
themes	fabt120330	1		1
plugins	fancy-box	1		1
plugins	fancybox-for-wordpress	1		1
plugins	fatpanda-facebook-comments	1		1
themes	Feather	2		1
plugins	featured-content-gallery	1		1
plugins	featured-image-widget	13		1
plugins	feed-them-social	1		1
plugins	fff-cron-manager	1		1
plugins	flagallery-skins	1		1
plugins	flash-album-gallery	1		1
plugins	follow-my-blog-post	2		1
plugins	foogallery-owl-carousel-template	1		1
themes	frantic	1		1
themes	freprotheme	1		1
themes	fsp0114	1		1
plugins	g-c-w	1		1
plugins	g-pre-g	1		1
plugins	gallery-widget	1		1
plugins	gcf	2		1
themes	gdwifa	1
themes	gdwifa20140303	2		1
themes	genesis	31
themes	genesis-2.1.3	1		1
themes	genesis-2.2.0	1		1
themes	genesis-2.2.3	1		1
themes	genesis-2.2.6	1		1
themes	genesis-2.2.7	1		1
themes	genesis-a2z	4			1
themes	genesis-aati	1		1
themes	genesis-broken	1		1
themes	genesis-bw	3
themes	genesis-cc0512	1
plugins	genesis-enews-extended	1		1
themes	genesis-gdw	2		1
plugins	genesis-header-nav-develop	1		1
themes	genesis-hehall	1
themes	genesis-hm	5
themes	genesis-hms	1		1
themes	genesis-image	6			1
themes	genesis-image-pregit	1		1
themes	genesis-odea	3		1
themes	genesis-oik	14			1
themes	genesis-paap	2		1
themes	genesis-sample	1		1
themes	genesis-SB	3
themes	genesis-tags	2
themes	genesis-v2.2.6	2		1
plugins	genesis-variable-footer-widgets	1		1
themes	genesis-wbwb	1		1
plugins	getver	1		1
themes	gkz1116	1		1
plugins	GlotPress-WP	1		1
themes	goodtheme-lead	1		1
plugins	google-analytics-for-wordpress	46		1
plugins	google-analytics-for-wordpress-renamed	1		1
plugins	google-sitemap-generator	15		1
plugins	gravity-forms-custom-post-types	1		1
plugins	gravityformsmailchimp	1		1
plugins	greprecated	4			1
themes	gsph1103	1		1
themes	gta0422	1		1
themes	gta0614	1		1
themes	gta0621	1		1
themes	gta0722c	2		1
plugins	gutenberg-2.0.0	1		1
plugins	gutenberg-2.1.0	2		1
plugins	gutenberg-2.3.0	2		1
plugins	gutenberg-course	2		1
themes	heft0204	1		1
themes	heft0205	2		1
themes	heft1229	1		1
themes	heft1229c	2		1
themes	heft1229gc	1		1
plugins	hello	2		1	1
plugins	hello-dolly	5
themes	hm120129	3		1
themes	hm120206	4		1
themes	hm120206c	4		1
themes	hm140702	2		1
themes	hms0820	2		1
themes	hms0826	2		1
themes	hms0906	2		1
themes	hms0907	2		1
themes	hsoh0914	4		1
themes	hsoh0914a	4		1
themes	hsoh0922	4		1
themes	hsoh0922bp	1		1
themes	hsoh0928bp	3		1
themes	hsoh1015	1		1
themes	hsoh1027bp	4		1
plugins	html5-slideshow-presentations	1		1
plugins	hyperdb	1		1
plugins	image-store	1		1
themes	imbalance	1		1
plugins	import-html-pages	1		1
plugins	import-users-from-csv-renamed	1		1
themes	in-the-beginning	1		1
plugins	inc	1		1
plugins	infolinks-officlial-plugin	1		1
plugins	infusionsoft-web-tracker	1		1
themes	Innova	1		1
plugins	instagram-image-gallery	1		1
themes	InterPhase	2		1
plugins	iphone-images	1		1
plugins	issue-19	2		1
plugins	issue-49	1		1
themes	japics1102	2		1
plugins	jetpack-3.9.4	2		1
plugins	jetpack-easy-playlists	1		1
plugins	jetpack-extras	1		1
plugins	jetpack-renamed	1		1	1
themes	journal	2		1
plugins	jquery-featured-content-gallery	2		1
themes	jquery-UI	1		1
themes	jquery-ui-1.12.1.custom	1		1
themes	jquery-ui-themes-1.12.1	1		1
plugins	json-rest-api	2		1
plugins	kiwi-logo-carousel	1		1
themes	lalu0915	1		1
themes	lalu1223	2		1
themes	li020226	1		1
themes	lifestyle	1		1
plugins	lightbox-plus	2		1
plugins	live-composer-page-builder	1		1
plugins	log-urgh	1		1
plugins	logo-carousel	1		1
plugins	logo-carousel-slider	1		1
plugins	mad-mimi-broken	1		1
themes	Magnificent	1		1
themes	Martha	1		1
themes	Martha1	1		1
themes	match	1		1
themes	maximus	2		1
themes	maximus-rf	2		1
themes	mdt1209	1		1
themes	minimalist-pro	2		1
themes	minn-lite	1		1
themes	modernbloggerpro	1		1
plugins	more-privacy-options	3		1
plugins	motors-car-dealership-classified-listings	1		1
plugins	mtouch-quiz	1		1
plugins	multi-site-plugins-add-new	1		1
plugins	my-page-order	1		1
plugins	my-plugin	1		1	1
plugins	my-wp-health-check	1		1
plugins	myplugins	1		1
themes	mystile	1		1
plugins	network-privacy	6		1
plugins	nextgen-gallery	13		1
themes	nivo2011	5		1
themes	nivoblackbird	1		1
themes	no-sidebar-pro	2		1
themes	Nominal	1		1
themes	novo	1		1
plugins	ns-cloner-site-copier	2		1
themes	nuance-v1.2.3	1		1
themes	nuance-v1.2.4	1		1
plugins	OAuth1	1		1
plugins	OAuth1-master	1		1
plugins	official-statcounter-plugin-for-wordpress	2		1
plugins	oik-2.5	1		1
plugins	oik-3.0.1	1		1
plugins	oik-3.0.2	1		1
plugins	oik-a2z-pregit	1		1
plugins	oik-api	1		1
plugins	oik-batch-pre-resolving-cd-problem	2		1	1
plugins	oik-batch-pregit	1		1
plugins	oik-batch-renamed	2		1
plugins	oik-bbpress-ren	2		1
plugins	oik-blogger-importer	3		1
plugins	oik-bob-bing-wide-1.21	1		1
plugins	oik-bob-bing-wide-1.30.2	1		1
plugins	oik-bwtrace-2.0.11	1		1
plugins	oik-bwtrace-2.0.12	1		1
plugins	oik-bwtrace-2.0.6	1		1
plugins	oik-bwtrace-git	1		1	1
plugins	oik-bwtrace-ren	1		1
plugins	oik-bwtrace-renamed	1		1
plugins	oik-bwtrace-too-new-for-oik-2.5	1		1
plugins	oik-bwtrace-v2.0.11	1		1
plugins	oik-bwtrace.2.0.11	1		1
plugins	oik-bwtrace.php	1		1
plugins	oik-bwtracev2.0.12	1		1
plugins	oik-clone-20171114	2		1	1
plugins	oik-content	2		1
plugins	oik-css-broken-1029	1		1
plugins	oik-css-git-clone	2		1	1
plugins	oik-css-pregit	2		1
plugins	oik-edd-but-no-edd	1		1
plugins	oik-external-link-warning-pregit	1		1
plugins	oik-f	1		1
plugins	oik-fields-1.36	1		1
plugins	oik-fields-pregit	1		1
plugins	oik-fields-ren	1		1
plugins	oik-fields-renamed	2		1
plugins	oik-fields.x	1		1
plugins	oik-getimage	1		1
plugins	oik-git-clone	1		1	1
plugins	oik-jquery	1		1
plugins	oik-l10n	1		1
plugins	oik-mailchimp	1		1
plugins	oik-make	1		1
plugins	oik-ms-renamed	1		1
plugins	oik-nivo-slider-1.3	1		1
plugins	oik-nivo-slider-renamed	1		1
plugins	oik-policies	1		1
plugins	oik-popup-saved	1		1
plugins	oik-pregit	1		1
plugins	oik-privacy-policy.php	1		1
plugins	oik-ren	1		1
plugins	oik-renamed	2		1
plugins	oik-rwd-ren	1		1
plugins	oik-rwd-renamed	1		1
plugins	oik-sc-help-1.9	1		1
plugins	oik-sc-help-renamed	1		1
plugins	oik-shutdown	1		1
plugins	oik-signup-user-notification	1		1
plugins	oik-squeeze-pregit	1		1
plugins	oik-types-1.6	1		1
plugins	oik-types-pregit	1		1
plugins	oik-types-renamed	1		1
plugins	oik-types-v1.6	1		1
plugins	oik-user-v0.5	1		1
plugins	oik-v2.6-alpha.0525	1		1
plugins	oik-wcs-renamed	1		1
plugins	oik-weight-zone-shipping-pro-0.1.0	1		1
plugins	oik-weight-zone-shipping-pro-v0.1.0	1		1
plugins	oik-weight-zone-shipping-pro-v0.2.2	1		1
plugins	oik-weightcountry-shipping-pro-v1.4.1	1		1
plugins	oik-wzs-rates-pregit	1		1
themes	oik0808	3		1
themes	oik0819c	3		1
themes	oik0917	1		1
themes	oik0917c	1		1
themes	oik0917r	1		1
themes	oik0917s	1		1
themes	oik0917t	4		1
themes	oik0918	3		1
themes	oik120206	1		1
themes	oik120206c	1		1
themes	oik120815	1		1
themes	oik2012	7		1
themes	oik20120	5		1
themes	oik310816	5		1
themes	oik310816c	4		1
themes	oik310816c-buggered	1		1
themes	oik401126	1		1
themes	oik401126-art4	1		1
themes	oik410130	4		1
themes	oik410130-1.1	2		1
themes	oik410130c	4		1
themes	oik410130c-1.1	2		1
themes	oik410326	2		1
themes	oik410923	4		1
themes	oik410923c	1		1
themes	oik420130	1		1
themes	oik420130lm	1		1
themes	oik420130wp	1		1
themes	olc0618	2		1
themes	olc120815	2		1
themes	olc120815c	3		1
themes	olc130611	1		1
plugins	oldplay	2		1
themes	omg	1		1
themes	one-pager-genesis-master	1		1
themes	oobit	6		1
themes	oobit v1.0	1		1
themes	oobit-extras	1		1
plugins	opcache	1		1
plugins	owl-carousel	1		1
plugins	owzs-pro	1		1
themes	p2	1		1
plugins	page-tree	1		1
themes	parallax-pro	5		1
plugins	paypal-responder	1		1
themes	pcs0809	1		1
themes	pcs0822	1		1
themes	pcs1003	1		1
themes	pcs1013	1		1
themes	pcs20141209	1		1
themes	personaltrainer	2		1
themes	phoenix0516	1		1
plugins	php71-fixes	1		1	1
plugins	php72-fixes	1		1	1
plugins	phpunit	3		1	1
themes	pictorico	1		1
themes	pinboard	1		1
plugins	play-rel1	2		1
plugins	play-rel2	2		1
plugins	played	1		1
themes	pob1028	1		1
plugins	pods	2		1
plugins	popdom-themes-backup	1		1
plugins	PostMeta	1		1
plugins	promotion-slider	1		1
themes	psc0211	1		1
themes	PureType	2		1
plugins	qtranslate-x	1		1
plugins	quick-pagepost-redirect-plugin	2		1
themes	rcgc0318	1		1
themes	rcgc0818	1		1
themes	rcr0725	2		1
themes	rctc0130	2		1
themes	rcwd0415	1		1
plugins	recent-global-posts-widget	1		1
plugins	relocateme	1		1
themes	responsive	1		1
plugins	rest-api	2		1
plugins	resume-submissions-job-postings	1		1
themes	retro-fitted	1		1
themes	retro-fitted-child	1		1
themes	rf0122	1		1
themes	rf0202	2		1
themes	rf0227	2		1
themes	rf0227c	2		1
themes	rf0311	5		1
themes	rf0311c	4		1
themes	rf0403	2		1
themes	rf0403c	2		1
themes	rf0510	2		1
themes	rf0510c	3		1
plugins	rjd	1		1
themes	rjdap	2		1
themes	rjdap-0.0.3	1		1
themes	rjdap-clone	1		1
themes	rjdpp	1		1
themes	rmt4dws	1		1
themes	rngs0414	3		1
themes	rngs0414c	3		1
themes	rngs0721	2		1
themes	rngs0721-ren	1		1
themes	rngs0721-wtf	1		1
themes	rngs0721c	2		1
themes	rngs0827	2		1
themes	rockstar	1		1
themes	royal	1		1
plugins	s2member-files	4		1
plugins	s2member-logs	4		1
themes	s2s0515	2		1
themes	s2s0515c	2		1
plugins	sample	1		1
plugins	saved_plugins	1		1
themes	sb0515	2		1
themes	sb1028	1		1
themes	sb2010	1		1
themes	sb2010_wm	1		1
themes	scr0909	3		1
themes	sds_2012	1		1
plugins	searchterms-tagging-2	2		1
plugins	seo-automatic-links	1		1
plugins	sexybookmarks	8		1
plugins	sexybookmarks-broke	1		1
themes	sh0412	1		1
themes	sh0612	1		1
plugins	share-this	1		1
plugins	shareadraft-master	1		1
themes	shell-lite	1		1
plugins	Shortcake	3		1
plugins	shortcake-gutenberg	3		1
plugins	shortcode-reference	1		1
plugins	si-captcha-for-wordpress	11		1
plugins	simple-facebook-connect	6		1
plugins	simple-image-widget	2		1
plugins	simple-twitter-connect	6		1
themes	simplest	1		1
themes	siteground-wp23	1		1
themes	siteground-wp63	1		1
themes	siteground-wp73	1		1
plugins	sitemap-redirect	1		1
themes	sleekphoto	1		1
plugins	slide-in	1		1
plugins	slideshow-gallery-2	1		1
plugins	slideshow-gallery-pro	3		1
plugins	slideshow-manager	1		1
plugins	sliding-youtube-gallery	1		1
plugins	smart-google-code-inserter	1		1
plugins	sociable-broken	1		1
themes	sol121012	2		1
themes	sol121012c	2		1
themes	sol150508	2		1
themes	sorbet	2		1
plugins	spam-destroyer	1		1
plugins	spam-reg-check	4		1
themes	spartan	1		1
plugins	sql-csv	1		1
themes	st0515	1		1
themes	storefront	4		1
themes	style	1		1
plugins	sub-page-summary	4		1
plugins	subpages-widget	1		1
themes	superhero	1		1
themes	survive0310	4		1
themes	survive0310-art4	1		1
themes	survive1120	2		1
themes	survive1210	2		1
themes	symondson0903	1		1
themes	symondson0903c	1		1
themes	szerelmey	1		1
themes	t10scom0201	1		1
themes	t10scom120128	1		1
themes	t40	1		1
plugins	test-41257	1		1	1
plugins	testapi	1		1
plugins	testimonials-by-woothemes	1		1
plugins	thank-me-later	1		1
themes	thematic	1		1
themes	theme465	1		1
plugins	themes	1		1
themes	thesis_16	1		1
plugins	tides	1		1
themes	tl0515	1		1
plugins	transposh-translation-filter-for-wordpress	1		1
themes	trcg120403	3		1
themes	trcg120403c	3		1
themes	trcg121026	1		1
themes	Trim	2		1
themes	trtc0104	1		1
themes	trtc0212	1		1
themes	trtc0225	1		1
themes	trtc0225c	1		1
themes	trtc1230	1		1
themes	twenty-seven-pro	2		1
themes	twentyeleven	57		1
themes	twentyeleven-2.1	1		1
themes	twentyfifteen	43		1
themes	twentyfifteen-v1.7	1		1
themes	twentyfourteen	51		1
themes	twentyseventeen	26		1
themes	twentysixteen	23		1
themes	twentysixteen-symlinked-gitted	1		1
themes	twentyten	56		1
themes	twentythirteen	53		1
themes	twentytwelve	57		1
plugins	twentytwelve-copied-from-theme	1		1
plugins	u-buddypress-forum-editor	1		1
themes	uf-scribe	1		1
themes	uf-spirit	1		1
plugins	ultimate-tinymce	3		1
plugins	ultimate-tinymce-7	1		1
themes	Universe	1		1
plugins	unserialize	1		1
themes	Untitled	1		1
themes	upfront	1		1
themes	vantage	2		1
plugins	vc-extensions-bundle	1		1
plugins	visualizer	1		1
themes	wbwb20141021	2		1
plugins	wc-call-for-price	1		1
plugins	what-would-seth-godin-do	2		1
plugins	wmdum	1		1
themes	wonderflux	1		1
plugins	wonderplugin-carousel	1		1
plugins	wonderplugin-carousel-9.8	1		1
plugins	woocommerce-2.5.2	1		1
plugins	woocommerce-2.6	1		1
plugins	woocommerce-2.6.12	1		1
plugins	woocommerce-2.6.6	1		1
plugins	woocommerce-3.0	1		1
plugins	woocommerce-currency-switcher	1		1
plugins	woocommerce-extra-charges-to-payment-gateways	2		1
plugins	woocommerce-multilingual	2		1
plugins	woocommerce-product-archive-customiser	1		1
plugins	woocommerce-weight-country-based-shipping	1		1
plugins	woocommerce-wholesale-prices	2		1
plugins	woocommerce-wholesale-prices-premium	2		1
plugins	wordpress-beta-tester	6		1
plugins	wordpress-custom-post-type-archive	1		1
plugins	wordpress-develop-tests-svn-symlink	1		1
plugins	WordPress-Importer	3		1	1
plugins	wordpress-mu-domain-mapping	5
plugins	wordpress-mu-domain-mapping-disabled	1		1
plugins	wordpress-mu-domain-mapping-disabled-again	1		1
plugins	wordpress-mu-domain-mapping-local	1		1
plugins	wordpress-mu-domain-mapping-qw	1		1
plugins	wordpress-mu-domain-mapping-renamed	3		1
plugins	wordpress-mu-domain-mapping-renamed-again	1		1
plugins	wordpress-popup	1		1
plugins	wordpress-seo	66		1
plugins	wordpress-simple-survey	1		1
plugins	wordpress-social-login	2		1	1
themes	workstation-pro	2		1
themes	World	1		1
plugins	worldlogger-live-web-analytics	1		1
plugins	wp-browscap	1		1
plugins	wp-charts	2		1
plugins	wp-cli	5		1	1
plugins	wp-custom-cssjs	1		1
plugins	wp-custom-taxonomy-meta	1		1
plugins	wp-db-backup-made	1		1
plugins	wp-downloads	1		1
plugins	wp-email-login	2		1
plugins	wp-google-maps	2		1
plugins	wp-mail-smtp	4		1
plugins	wp-migrate-db-0.9	1		1
themes	wp-pompey	3		1
plugins	wp-responder-email-autoresponder-and-newsletter-plugin	1		1
plugins	wp-seo-qtranslate-x	1		1
plugins	wp-simplemail	1		1
plugins	wp-smush-pro	1		1
plugins	wp-smushit	2		1
plugins	wp-smushit.hold	1		1
plugins	wp-spamfree-7	1		1
plugins	wp-super-cache	6		1
plugins	wp-super-simple-speed	1		1
plugins	wp-top12	5			1
plugins	wpaudio-mp3-player	10		1
themes	wpg0216	4		1
themes	wpg0216bp	2		1
themes	wpg0216bp-renamed	1		1
plugins	wpgmappity	1		1
plugins	wpml-media	2		1
plugins	wpml-string-translation	2		1
plugins	wpml-translation-management	2		1
plugins	wpmu-dev-plusone	1		1
plugins	wpmudev-updates	6		1
themes	wporg-developer	1		1
plugins	wpremote	1		1	1
plugins	WPRobot3	1		1
plugins	wpseo-local	1		1
plugins	wysija-newsletters	4		1
plugins	wysija-newsletters-norty	1		1
plugins	y	1		1
themes	yellow0117	1		1
themes	yellowbrand	1		1
themes	yellowbrand-oik	1		1
plugins	yith-woocommerce-wishlist	1		1
plugins	youtube-embed-plus	1		1
plugins	zero_tolerance	1		1

## opinions
Editor	Mandatory	Level	Opinion	Action
A	O	S	WordPress version OK
C	Mandatory	S	WordPress <= 4.9	Update WordPress

## Hours
Parameter count to Size to Hours				Total hrs	7	21	42
Count	Size	Hours		Task	Small	Med	Large
0	Small	7		Design/spec	1	3	7
1	Small	7		Code	2	7	14
2	Small	7		Test	2	7	14
3	Small	7		Document	1	3	6
4	Small	7		Release	1	1	1
5	Med	21
6	Med	21		Days	1	3	6
7	Med	21
8	Med	21
9	Med	21
10	Med	21
11	Med	21
12	Med	21
13	Med	21
14	Med	21
15	Med	21
16	Med	21
17	Large	42
18	Large	42
19	Large	42
20	Large	42
21	Large	42
22	Large	42
23	Large	42
24	Large	42
25	Large	42
26	Large	42
27	Large	42
28	Large	42
29	Large	42
30	Large	42